## Menu
Dashboard: Georgia - HIV / AIDS
HIV / AIDS NFM, N/A | Grant No.: GEO-H-NCDC
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Georgia - HIV / AIDS
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, June 2007) | Measurement | Data Source
KP-1d(M): Percentage of people who inject drugs reached with HIV prevention programs - defined package of services | Numerator: Number and of IDUs reached by HIV/AIDS prevention programs during the last 6 months. Denominator: Estimated number of IDUs in the country The last available result and final target represents the number based on first 6 month of 2015. The beneficiary is considered reached if received at least two services from the list of basic package (condom, consultation, information materials, syringe/needle) and one of them has to be syringe/needleI at least once within a 6 month period. Clients' participation in informational events on HIV/AIDS awareness and safe behavior can be regarded as counseling. In addition beneficiaries can also receive other services (HIV, STIs, HBV, HCV testing, a referral to another specialists, and others) depending on the client’s needs. Targets for Jan-June are 6 month targets and Jul-Dec are 12 month targets (annual targets). Results of performance for period Jan -Jun 2017 - target 21570, will be reported in Febduary 2018 together with the results for July - Dec 2017 period. Results of performance for period Jan -Jun 2018 - target 23310, will be reported in Febduary 2019 together with the results for July - Dec 2018 period. | N-Non-cumulative | Programatic data (database)
KP-3d(M): Percentage of people who inject drugs that have received an HIV test during the reporting period and know their results | Targets represent number of people reached with VCT during each semi-annula period. The baseline represents the last available result for the first six months of 2015. Targets for Jan-June are 6 month targets and Jul-Dec are 12 month targets (annual targets) Results of performance for period Jan -Jun 2017 - target 19482, will be reported in Febduary 2018 together with the results for July - Dec 2017 period. Results of performance for period Jan -Jun 2018 - target 20874, will be reported in Febduary 2019 together with the results for July - Dec 2018 period. | N-Non-cumulative | Programatic data (database)
KP-1a(M): Percentage of MSM reached with HIV prevention programs - defined package of services | Numerator: Number and of MSM reached by HIV/AIDS prevention programs during the last 6 months. Denominator: Estimated number of MSM in the country, based on the MSM size estimateion study conducted in 2014. The last available result and final target represents the number based on first 6 month of 2015. MSM is considered to be reached with HIV prevention programs if received at least two services from the list of basic package (provision of condoms, lubricants, counseling and information materials) and one of them has to be condom at least once within a 6 month period. Clients' participation in informational events on HIV/AIDS awareness and safe behavior can be regarded as counseling. In addition beneficiaries can also receive other services (HIV, STIs, a referral to another specialists, and others) depending on the client’s needs. Targets for Jan-June are 6 month targets and Jul-Dec are 12 month targets (annual targets). Results of performance for period Jan -Jun 2017 - target 4165, will be reported in Febduary 2018 together with the results for July - Dec 2017 period. Results of performance for period Jan -Jun 2018 - target 5950, will be reported in Febduary 2019 together with the results for July - Dec 2018 period. | N-Non-cumulative | Programatic data (database)
KP-3a(M): Percentage of MSM that have received an HIV test during the reporting period and know their results | Targets represent number of people reached with VCT during each semi-annula period. The baseline represents the last available result for the first six months of 2015. Targets for Jan-June are 6 month targets and Jul-Dec are 12 month targets (annual targets). Results of performance for period Jan -Jun 2017 - target 2550, will be reported in Febduary 2018 together with the results for July - Dec 2017 period. Results of performance for period Jan -Jun 2018 - target 4080, will be reported in Febduary 2019 together with the results for July - Dec 2018 period. | N-Non-cumulative | Programatic data (database)
KP-other 1: Percentage of other vulnerable populations that have received an HIV test during the reporting period and know their results (prisoners) | The baseline represents the last available result for the first six months of 2015. Targets for Jan-June are 6 month targets and Jul-Dec are 12 month targets (annual targets). Numerators and Denominators will be reported during PU and PUDR.Results of performance for period Jan -Jun 2017 - target 4025, will be reported in Febduary 2018 together with the results for July - Dec 2017 period. Results of performance for period Jan -Jun 2018 - target 4375, will be reported in Febduary 2019 together with the results for July - Dec 2018 period. | N-Non-cumulative | Programatic Data
KP-1c(M): Percentage of sex workers reached with HIV prevention programs - defined package of services | Numerator: Number and of FSW reached by HIV/AIDS prevention programs during the last 6 months. Denominator: Estimated number of FSW in the country The last available result and final target represents the number based on first 6 month of 2015. The beneficiary is considered reached if received at least two services from the list of basic package (condom, information materials and counseling) and one of them has to be condom at least once within a 6 month period. Clients' participation in informational events on HIV/AIDS awareness and safe behavior can be regarded as counseling. In addition beneficiaries can also receive other services (HIV, STIs, HBV, HCV testing, a referral to another specialists, and others) depending on the client’s needs.Targets for Jan-June are 6 month targets and Jul-Dec are 12 month targets (annual targets). Results of performance for period Jan -Jun 2017 - target 2285, will be reported in Febduary 2018 together with the results for July - Dec 2017 period. Results of performance for period Jan -Jun 2018 - target 2741, will be reported in Febduary 2019 together with the results for July - Dec 2018 period. | N-Non-cumulative | Programatic data (database)
KP-3c(M): Percentage of sex workers that have received an HIV test during the reporting period and know their results | Targets represent number of people reached with VCT during each semi-annula period. The baseline represents the last available result for the first six months of 2015. Targets for Jan-June are 6 month targets and Jul-Dec are 12 month targets (annual targets). Results of performance for period Jan -Jun 2017 - target 1827, will be reported in Febduary 2018 together with the results for July - Dec 2017 period. Results of performance for period Jan -Jun 2018 - target 2285, will be reported in Febduary 2019 together with the results for July - Dec 2018 period. | N-Non-cumulative | Programatic data (database)
TCS-1(M): Percentage of people living with HIV currently receiving antiretroviral therapy | Country adopted treat all policy, which implies offering ART to all people who are already diagnosed with HIV. Because of high rates of late HIV diagnosis in Georgia the majority of our patinets have been already eligible for ART at previous CD4<500 recommendations. Switch to treat all policy in second half of 2015 did not dramatically increase the number of people on ART. Proposed scale-up is in line with propsoed coverage with HIV testing of key populaltions and takes into account existing dynamics in HIV diagnosis. Currently approximately 40% of people living with HIV remian undiagnosed and this is major problem. More prominent scale-up in ART coverage will require more prominent scale-up in HIV testing . Without further scale-up of testing forecasting more patients on ART is not realistic. Denominator for the baseline is updated also as before it was representing alligable for treatment PLHIV, now it represents estimated number of all PLHIV. | cummulative | AIDS Center HMIS
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Georgia |  | Title of the Grant: |  | Sustaining and Scaling up the Effective HIV/AIDS Prevention, Treatment and Care in Georgia
| Grant No.: | GEO-H-NCDC |  | Component: |  | HIV / AIDS | Total Funding: | 17962183.9927
| Principal Recipient: | NCDC |  |  | Round: | NFM | Phase: | N/A
| Start Date (dd/Mmm/yy): | 2016-07-01 |  | Local Fund Agent: |  | UNOPS
| Latest Rating: | B1 |  | Fund Portfolio Manager: |  | Tatyana Vinichenko
Information reporting period
| Report Period: | P12 | From: | 2019-04-01 | To: | 2019-06-30 | Date of entry of information: |  | 2019-08-20
| Prepared by: |  | Alexander Asatiani
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | $
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 1753207.6498
| Reporting period | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 3401736.7923
| Budget (in $) | 1753207.6498 | 1648529.1425 | 1203101.8906 | 2402502.8144 | 1065334.1016 | 1449595.2447 | 1017485.3641 | 1381972.7096 | 1452287.9959 | 1418021.7081 | 1678154.346 | 1491991.0253 | 96.37% |  |  | 4604838.6829
| Disbursements by GF (in $) | 1912231.72 | 2063549.52 | 1240552.15 | 2624740.47 | 160958.98 | 1362781.42 | 816070.3 | 1865698.14 | 1436247.95 | 1697024.4 | 1013726.22 | 1115896.53 |  |  |  | 7007341.4973
| Cumulative budget | 1753207.6498 | 3401736.7923 | 4604838.6829 | 7007341.4973 | 8072675.5989 | 9522270.8436 | 10539756.2077 | 11921728.9173 | 13374016.9132 | 14792038.6213 | 16470192.9674 | 17962183.9927 |  |  |  | 8072675.5989
| Cumulative disbursements | 1912231.72 | 3975781.24 | 5216333.39 | 7841073.86 | 8002032.84 | 9364814.26 | 10180884.56 | 12046582.7 | 13482830.65 | 15179855.05 | 16193581.27 | 17309477.8 |  |  |  | 9522270.8436
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 96.37% |  |  |  | 10539756.2077
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | P1: Cumulative Budget (in $); P2: Cumulative Expenditures (in $)
| Comprehensive prevention programs for MSM | P1: 1741903.0276; P2: 1534389.9817
| Comprehensive prevention programs for sex workers and their clients | P1: 1055637.0046; P2: 883215.6747
| Comprehensive prevention programs for people who inject drugs (PWID) and their partners | P1: 6178916.4568; P2: 5567454.9833
| Comprehensive programs for people in prisons and other closed settings | P1: 211917.9697; P2: 166259.6743
| Treatment, care and support | P1: 6152441.063; P2: 5593940.3347
| RSSH: Health management information systems and M&E | P1: 574528.9972; P2: 502515.6894
| Programs to reduce human rights-related barriers to HIV services | P1: 495799.8079; P2: 356584.744
| Program management | P1: 1118459.5019; P2: 991318.216
| PMTCT | P1: 51625.74; P2: 15548.5895
| RSSH: National health strategies | P1: 24991.5323; P2: 19596.6696
| HIV Testing Services | P1: 355962.8857; P2: 136711.7569
| Total | P1: 17962183.9867; P2: 15767536.3143; P4: OK: Data match
| F3: Disbursements and expenditures | [15 empty] | 11921728.9173
13374016.9132
|  | P1: Prior to reporting period; P2: Current reporting period; P3: Total Spent and Disbursement (in $) |  |  | 16470192.9674
| Disbursed by Global Fund | P1: 16193581.27; P2: 1115896.53; P3: 17309477.8
| PR expenditure and disbursement | P1: 5641030.4734; P2: 853515.5366; P3: 6494546.0101
| Disbursed to SRs | P1: 8474599.6922; P2: 798390.611; P3: 9272990.3032
| SR expenditures | P1: 8604788.4607; P2: 937839.3725; P3: 9542627.8332
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | P1: 60; P2: 60
| Days taken for disbursement to reach PR | P1: 45; P2: 15
| Days taken for disbursement to reach SRs | P1: 5; P2: 5
| Management Information: | P6: Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| NFM Grant Requirements | P2: 8; P3: 0; P4: 0; P5: 8
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 16; P2: 16; P3: 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding |  | 2 Projects |  |  | 2 Projects
| SRs | 7 | 7 | 7 | 7 | 7 | IDACIRC | HAPSF | GHRN | IMPHA | CIF | Equality | Tanadgoma
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 165; P2: 165; P3: 0
| SRs to PR | P1: 21; P2: 21; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | 621513.1396 | 273435.1973 | 56473.0836 | 1216941.6769 | 117643.1427 | 491331.5704 | 155982.9991 | 451430.0753 | 443391.2765 | 490313.3325 | 115373.8908 | 475512.776
| Obligations | 19935.614 | 1225173 | 224961.9076 | 599588.3184 | 580029.0709 | 131899.74 | 30591.66 | 42870.98 | 491507.3993 | 471954 | 429989.8458 | 693062
| Expenditures | 579569.0589 | 211125.8 | 417945 | 661579 | 252325 | 642504 | 152807 | 445495 | 169836 | 570007 | 89500 | 380637
| Budget Approved cumulative* | 621513.1396 | 894948.3369 | 951421.4204 | 2168363.0973 | 2286006.24 | 2777337.8104 | 2933320.8095 | 3384750.8848 | 3828142.1613 | 4318455.4938 | 4433829.3846 | 4909342.1606
| Obligations cumulative | 19935.614 | 1245108.614 | 1470070.5216 | 2069658.84 | 2649687.9109 | 2781587.6509 | 2812179.3109 | 2855050.2909 | 3346557.6903 | 3818511.6903 | 4248501.5361 | 4941563.5361
| Expenditures cumulative | 579569.0589 | 790694.8589 | 1208639.8589 | 1870218.8589 | 2122543.8589 | 2765047.8589 | 2917854.8589 | 3363349.8589 | 3533185.8589 | 4103192.8589 | 4192692.8589 | 4573329.8589
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets/mgs per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | Zidovudine/Lamivudine | 2 | 60 | 689 | 41340 | 456660 | 11.0464 | 6 | 5.0464
|  | Syringes (1ml) | 0.26 | 7.8 | 11000 | 85800 | 447018 | 5.21 | 3 | 2.21
|  | Condoms (Tanadgoma) | 0.6 | 18 | 4055 | 72990 | 439689 | 6.024 | 3 | 3.024
|  | Condoms (EM) | 1 | 30 | 390 | 11700 | 51984 | 4.4431 | 3 | 1.4431
| Programmatic Information: | P9: Enter performance data in every yellow cell.
|  | P6: Jul-Sep 2016; P7: Oct-Dec 2017; P8: Jan-Mar 2017; P9: Jan-Jun 2017; P10: Jan-Sep 2017; P11: Jan-Dec 2017; P12: Jan-Mar 2018 | Apr- Jun 2018 | Jul-Sep 2018 | Jan-June 2018 | Jan-Apr 2019
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Percentage of PWID that have received an HIV test during the reporting period and know their results |  |  | KP-3d | Yes | Target | 25347 | 25347 | 6958 | 13916 | 20874 | 27832 | 7875 | 15750 | 23625 | 31500 | 8531.25 | 17062.5
[6 empty] | Achieved | 22099 | 28279 | 7219 | 16129 | 18626 | 26294 | 5762 | 11859 | 23914 | 24421 | 8173 | 16211
| Percentage of MSM reached with HIV prevention programs - defined package of services |  |  | KP-1a | Yes | Target | 4250 | 4250 | 1487.5 | 2975 | 4462.5 | 5950 | 2125 | 4250 | 6375 | 8500 | 2081.25 | 4162.5
[6 empty] | Achieved | 3167 | 3826 | 1383 | 2314 | 3126 | 3846 | 1857 | 3464 | 5523 | 7104 | 2404 | 4847
| Percentage of people living with HIV currently receiving antiretroviral therapy |  |  | TCS-1 | Yes | Target | 4000 | 4000 | 4550 | 4550 | 4550 | 4550 | 5100 | 5100 | 5100 | 5100 | 5500 | 5500
[6 empty] | Achieved | 3518 | 3638 | 3786 | 3899 | 4100 | 4144 | 4260 | 4365 | 4468 | 4597 | 4136 | 4798
| Percentage of PWID reached with HIV prevention programs - defined package of services |  |  | KP-1d | Yes | Target | 28329 | 28329 | 7703.5 | 15407 | 23110.5 | 30814 | 8793.75 | 17587.5 | 26381.25 | 35175 | 9187.5 | 18375
[6 empty] | Achieved | 26928 | 30330 | 13968 | 20114 | 23118 | 27250 | 14112 | 20290 | 16318 | 29891 | 16853 | 24934
| Percentage of MSM that have received an HIV test during the reporting period and know their results |  |  | KP-3a | Yes | Target | 3060 | 3060 | 1062.5 | 2125 | 3187.5 | 4250 | 1700 | 3400 | 5100 | 6800 | 1387.5 | 2775
[6 empty] | Achieved | 1597 | 2035 | 1114 | 1981 | 2968 | 3889 | 925 | 2079 | 3226 | 4637 | 1393 | 2557
| Percentage of sex workers reached with HIV prevention programs - defined package of services |  |  | KP-1c | Yes | Target | 2610 | 2610 | 815.75 | 1631.5 | 2447.25 | 3263 | 1076.5 | 2153 | 3229.5 | 4306 | 975 | 1950
[6 empty] | Achieved | 2479 | 3160 | 1532 | 2372 | 2885 | 3367 | 1593 | 2476 | 3229 | 3844 | 1716 | 2935
| Percentage of sex workers that have received an HIV test during the reporting period and know their results |  |  | KP-3c | Yes | Target | 1958 | 1958 | 652.5 | 1305 | 1957.5 | 2610 | 897.25 | 1794.5 | 2691.75 | 3589 | 731.25 | 1462.5
[6 empty] | Achieved | 1562 | 2111 | 712 | 1296 | 1735 | 2185 | 681 | 1325 | 1971 | 2698 | 685 | 1393
| Percentage of other vulnerable populations (prisoners) that have received an HIV test during the reporting period and know their results |  |  | KP-3e | Yes | Target | 5500 | 5500 | 1500 | 3000 | 4500 | 6000 | 1625 | 3250 | 4875 | 6500 | 2345 | 2345
[6 empty] | Achieved | 4718 | 6068 | 1552 | 2937 | 4226 | 5534 | 1605 | 2611 | 4122 | 5978 | 1637 | 3073
Target
Achieved
Target
Achieved
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Percentage of PWID that have received an HIV test during the reporting period and know their results |  |  | KP-3d | Yes | Target | 25347 | 25347 | 6958 | 13916 | 20874 | 27832 | 7875 | 15750 | 23625 | 31500 | 8531.25 | 17062.5
[6 empty] | Achieved | 22099 | 28279 | 7219 | 16129 | 18626 | 26294 | 5762 | 11859 | 23914 | 24421 | 8173 | 16211
| Percentage of MSM reached with HIV prevention programs - defined package of services |  |  | KP-1a | Yes | Target | 4250 | 4250 | 1487.5 | 2975 | 4462.5 | 5950 | 2125 | 4250 | 6375 | 8500 | 2081.25 | 4162.5
[6 empty] | Achieved | 3167 | 3826 | 1383 | 2314 | 3126 | 3846 | 1857 | 3464 | 5523 | 7104 | 2404 | 4847
| Percentage of people living with HIV currently receiving antiretroviral therapy |  |  | TCS-1 | Yes | Target | 4000 | 4000 | 4550 | 4550 | 4550 | 4550 | 5100 | 5100 | 5100 | 5100 | 5500 | 5500
[6 empty] | Achieved | 3518 | 3638 | 3786 | 3899 | 4100 | 4144 | 4260 | 4365 | 4468 | 4597 | 4136 | 4798
Menu
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B75: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B76: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B82: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B97: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.

## Grant Detail
Dashboard: Georgia - HIV / AIDS
Country: | Georgia |  | Title of the Grant: |  | Sustaining and Scaling up the Effective HIV/AIDS Prevention, Treatment and Care in Georgia
Component: | HIV / AIDS | Grant No. | GEO-H-NCDC | Start Date: |  | 2016-07-01 | Total Funding | 17962183.9927
Round: | NFM | Phase: | N/A | Principal Recipient: |  | NCDC
Report Period: | P12 | from: | 2019-04-01 | to: |  | 2019-06-30 | Latest Rating: | B1
Local Fund Agent: | UNOPS |  |  | Fund Portfolio Manager: |  | Tatyana Vinichenko
Prepared by: | Alexander Asatiani |  |  | Report preparation date: |  | 2019-08-20
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Georgia - HIV / AIDS
NFM | N/A |  |  |  | Report Period: |  | P12
Latest Rating: | B1 |  | NCDC |  | From: |  | 2019-04-01
|  | Sustaining and Scaling up the Effective HIV/AIDS Prevention, Treatment and Care in Georgia |  |  |  | To: | 2019-06-30
Financial Indicators
F1: Budget and disbursements by Global Fund - in ($) Report Period: P12 |  |  |  | F3: Disbursements and expenditures - in ($) Report Period: P12
Comments: |  |  |  | Comments:
F2: Budget and actual expenditures by Grant Objective - in ($) Report Period: P12 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P12
Comments: |  |  |  | Comments:
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 60 | 60
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 15
|  |  |  | Days taken for disbursement to reach SRs |  | 5 | 5
Menu

## Management
Dashboard: Georgia - HIV / AIDS
NFM | N/A |  |  |  |  | Report Period: |  | P12
Latest Rating: | B1 |  | NCDC |  |  | From: |  | 2019-04-01
|  | Sustaining and Scaling up the Effective HIV/AIDS Prevention, Treatment and Care in Georgia |  |  |  |  | To: | 2019-06-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P12 |  |  |  | M2: Status of key PR management positions Report Period: P12
Comments: |  |  |  | Comments:
M3: Contractual arrangements (SRs) Report Period: P12 |  |  |  | M4: Number of complete reports received on time Report Period: P12
Comments: |  |  |  | Comments:
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P12
Comments: |  |  |  | Comments:
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Zidovudine/Lamivudine | 11.0464 | 6 | 5.0464
[5 empty] | Syringes (1ml) | 11 | 3 | 8
[5 empty] | Condoms (Tanadgoma) | 6.024 | 3 | 3.024
[5 empty] | Condoms (EM) | 4.4431 | 3 | 1.4431 | Will be redistributed as needed from TG
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Georgia - HIV / AIDS
NFM | N/A | [7 empty] | Report Period: |  | P12
Latest Rating: | B1 |  | NCDC | [6 empty] | From: | 2019-04-01
|  | Sustaining and Scaling up the Effective HIV/AIDS Prevention, Treatment and Care in Georgia | [7 empty] | To: | 2019-06-30 | [6 empty] | Raiting |  | Valor
Programmatic Indicators
Percentage of PWID that have received an HIV test during the reporting period and know their results |  |  |  | Percentage of MSM reached with HIV prevention programs - defined package of services |  |  |  | Percentage of people living with HIV currently receiving antiretroviral therapy
Comment: P1 |  |  |  | Comment: P2 |  |  |  | Comment: P3
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  | min | 0 | 30% | 60% | 90% | 100% | min | 0 | 20% | 40% | 60% | 80%
Percentage of PWID that have received an HIV test during the reporting period and know their results |  |  | 17062.5 | 16211 | 95.01% | [6 empty] | max | 30% | 60% | 90% | 100% | 200% | max | 20% | 40% | 60% | 80% | 100%
Percentage of MSM reached with HIV prevention programs - defined package of services |  |  | 4162.5 | 4847 | 116.4% | [7 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | [5 empty] | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Percentage of people living with HIV currently receiving antiretroviral therapy |  |  | 5500 | 4798 | 87.24% |  |  | Annual Target |  |  |  |  | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A
Percentage of PWID reached with HIV prevention programs - defined package of services |  |  | 18375 | 24934 | 135.7% | [6 empty] | 25049 | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A
Percentage of MSM that have received an HIV test during the reporting period and know their results |  |  | 2775 | 2557 | 92.14% | [7 empty] | #N/A | #N/A | #N/A | [5 empty] | #N/A | #N/A | #N/A
Percentage of sex workers reached with HIV prevention programs - defined package of services |  |  | 1950 | 2935 | 150.5% | [7 empty] | #N/A | #N/A | #N/A
Percentage of sex workers that have received an HIV test during the reporting period and know their results |  |  | 1462.5 | 1393 | 95.25% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage of other vulnerable populations (prisoners) that have received an HIV test during the reporting period and know their results |  |  | 2345 | 3073 | 131% |  |  | Number of prison inmates |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage of individuals receiving Opioid Substitution Therapy who received treatment for at least 6 months |  |  |  |  | #DIV/0! | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Georgia - HIV / AIDS
NFM | N/A |  |  |  |  | Report Period: | P12
Latest Rating: | B1 |  | NCDC |  |  | From: | 2019-04-01
|  |  | Sustaining and Scaling up the Effective HIV/AIDS Prevention, Treatment and Care in Georgia |  |  | To: | 2019-06-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1
F2
F3
F4
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1
M2 |  |  | #DIV/0! | #DIV/0!
M3
M4
M5
M6
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend
P2 - trend
P3 - trend
P1
P2
P3 |  | Annual Target
P4
P5
P6
P7
P8 |  | Number of prison inmates
P9
P10
Menu

## Actions
Dashboard: Georgia - HIV / AIDS
| NFM | N/A |  |  |  | Report Period: |  | P12
| Latest Rating: | B1 |  | NCDC |  | From: |  | 2019-04-01
|  |  | Sustaining and Scaling up the Effective HIV/AIDS Prevention, Treatment and Care in Georgia |  |  |  | To: | 2019-06-30
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Georgia - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe