## Menu
Dashboard: Georgia - HIV / AIDS
HIV / AIDS Round 10, Phase 2 | Grant No.: GEO-H-NCDC
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Georgia - HIV / AIDS
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, June 2007) | Measurement | Data Source
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Georgia |  | Title of the Grant: |  | Sustaining and scaling up the existing national responses for implementation of effective HIV/AIDS prevention activities, improving survival rates of people with advanced HIV infection by strengthening treatment and care interventions
| Grant No.: | GEO-H-NCDC |  | Component: |  | HIV / AIDS | Total Funding: | 13771977
| Principal Recipient: | NCDC |  |  | Round: | Round 10 | Phase: | Phase 2
| Start Date (dd/Mmm/yy): | 2014-04-01 |  | Local Fund Agent: |  | UNOPS
| Latest Rating: | B1 |  | Fund Portfolio Manager: |  | Tsovinar Sakanyan
Information reporting period
| Report Period: | P2 | From: | 2014-07-01 | To: | 2014-09-30 | Date of entry of information: |  | 2014-10-05
| Prepared by: |  | Alexander Asatiani
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | $
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 2994963
| Reporting period | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 3961822
| Budget (in $) | P1: 2994963; P2: 966859; P3: 2403315; P4: 1897360; P5: 3349114; P6: 1949216; P7: 1000723 | 111.5% |  |  | 6365137
| Disbursements by GF (in $) | P1: 4418000; P2: 0 |  |  |  | 8262497
| Cumulative budget | 2994963 | 3961822 | 6365137 | 8262497 | 11611611 | 13560827 | 14561550 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11611611
| Cumulative disbursements | 4418000 | 4418000 | 4418000 | 4418000 | 4418000 | 4418000 | 4418000 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13560827
|  | 0% | 111.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 14561550
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | P1: Cumulative Budget (in $); P2: Cumulative Expenditures (in $)
| To establish supportive enviroment for HIV/AIDS prevention, treatment, care and support | P1: 0; P2: 0
| To increase coverage and quality of preventive interventions targeted at MARPs | P1: 2370008; P2: 966221.46
| To sustain treatment, care and support for PLHIV including Abkhazia frozen conflict area | P1: 1306873; P2: 284029.1663
| To generate evidences and document HIV program effectivness | P1: 153749; P2: 73081.5337
| PR Program Manangment | P1: 131192; P2: 66271.19
| Total | P1: 3961822; P2: 1389603.35; P4: OK: Data match
| F3: Disbursements and expenditures | [15 empty] | 0
0
|  | P1: Prior to reporting period; P2: Current reporting period; P3: Total Spent and Disbursement (in $) |  |  | 0
| Disbursed by Global Fund | P1: 4418100; P2: 0; P3: 4418100
| PR expenditure and disbursement | P1: 375319; P2: 1014284; P3: 1389603
| Disbursed to SRs | P1: 359229; P2: 959990; P3: 1319219
| SR expenditures | P1: 709423.2141; P2: 821762.9936; P3: 1531186.2077
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | P1: 45; P2: 45
| Days taken for disbursement to reach PR | P1: 45; P2: 0
| Days taken for disbursement to reach SRs | P1: 5; P2: 3
| Management Information: | P6: Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) | P2: 5; P3: 1; P4: 0; P5: 6
| Time Bound Actions (TBAs) | P2: 2; P3: 0; P4: 0; P5: 2
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 16; P2: 15; P3: 1
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 6; P2: 6; P3: 6; P4: 6; P5: 6
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 162; P2: 162; P3: 0
| SRs to PR | P1: 18; P2: 18; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 1831818; P2: 1774; P3: 1050104; P4: 562389; P5: 2132182; P6: 702864; P7: 1774
| Obligations | P1: 0; P2: 539689.597
| Expenditures | P1: 0; P2: 4114
| Budget Approved cumulative* | 1831818 | 1833592 | 2883696 | 3446085 | 5578267 | 6281131 | 6282905 | 6282905 | 6282905 | 6282905 | 6282905 | 6282905
| Obligations cumulative | 0 | 539689.597 | 539689.597 | 539689.597 | 539689.597 | 539689.597 | 539689.597 | 539689.597 | 539689.597 | 539689.597 | 539689.597 | 539689.597
| Expenditures cumulative | 0 | 4114 | 4114 | 4114 | 4114 | 4114 | 4114 | 4114 | 4114 | 4114 | 4114 | 4114
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | Zidovudine/Lamivudine | 2 | 60 | 619 | 37140 | 507720 | 13.6704 | 6 | 7.6704
|  | Methadone (Tab.Mg) | 40 | 1200 | 493 | 591600 | 4244357.6 | 7.1744 | 3 | 4.1744
|  | Condoms (FSW) | 0.6 | 18 | 1065 | 19170 | 69119 | 3.6056 | 3 | 0.60558
|  | Syringes (1ml) | 0.4 | 12 | 8962.5 | 107550 | 212310 | 1.9741 | 3 | -1.0259
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Number of MARPs (IDUs, MSM and FSWs) covered with HIV testing and counselling (including provision of results) |  |  | 1 | Yes | Target | P1: 7720; P2: 6795; P3: 7503; Enter performance data in every yellow cell. P4: 5975.6615; Enter performance data in every yellow cell. P5: 5975.6615; Enter performance data in every yellow cell. P6: 6345.3885; Enter performance data in every yellow cell. P7: 6345.3885
[6 empty] | Achieved | P1: 9770; P2: 5975
| Number and percentage of MSM reached with HIV prevention programmes - defined package of services |  |  | 2.1 | Yes | Target | P1: 945; P2: 680; P3: 748; Enter performance data in every yellow cell. P4: 990; Enter performance data in every yellow cell. P5: 990; Enter performance data in every yellow cell. P6: 1257.5; Enter performance data in every yellow cell. P7: 1257.5
[6 empty] | Achieved | P1: 346; P2: 620
| Number and percentage of eligible adults and children currently receiving antiretroviral therapy |  |  | 3 | Yes | Target | P1: 2330; P2: 2530; P3: 2740; Enter performance data in every yellow cell. P4: 3000; Enter performance data in every yellow cell. P5: 3000; Enter performance data in every yellow cell. P6: 3270; Enter performance data in every yellow cell. P7: 3270
[6 empty] | Achieved | P1: 2311; P2: 2410
| Number of prisoners covered with VCT (HIV testing and counselling, including provision of results) |  |  | 1.1 | Yes | Target | P1: 2250; P2: 1350; P3: 1500; Enter performance data in every yellow cell. P4: 1707.5; Enter performance data in every yellow cell. P5: 1707.5; Enter performance data in every yellow cell. P6: 1750; Enter performance data in every yellow cell. P7: 1750
[6 empty] | Achieved | P1: 2464; P2: 1311
| Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services |  |  | 1.2 | Yes | Target | bar: P1 to Enter performance data in every yellow cell. P12
Achieved | bar: P1 to Enter performance data in every yellow cell. P12
| Number and percentage of IDUs reached with HIV prevention programmes - defined package of services |  |  | 2.2 | Yes | Target | P1: 17523.75; P2: 12500; P3: 5425; Enter performance data in every yellow cell. P4: 9140.625; Enter performance data in every yellow cell. P5: 9140.625; Enter performance data in every yellow cell. P6: 9318.75; Enter performance data in every yellow cell. P7: 9318.75
[6 empty] | Achieved | P1: 1910; P2: 1729
| Number and percentage of FSWs reached with HIV prevention programmes - defined package of services |  |  | 2.3 | Yes | Target | P1: 1015; P2: 650; P3: 582; Enter performance data in every yellow cell. P4: 735; Enter performance data in every yellow cell. P5: 735; Enter performance data in every yellow cell. P6: 913.85; Enter performance data in every yellow cell. P7: 913.85
[6 empty] | Achieved | P1: 825; P2: 714
| Percentage of individuals receiving OST who received treatment for at least 6 months |  |  | 2.4 | Yes | Target | P1: 420; P2: 450; P3: 450; Enter performance data in every yellow cell. P4: 480; Enter performance data in every yellow cell. P5: 480; Enter performance data in every yellow cell. P6: 600; Enter performance data in every yellow cell. P7: 600
[6 empty] | Achieved | P1: 420; P2: 427
| Percentage of adults and children that initiated ART, with an undetectable viral load at 12 months (<1000 copies/ml) |  |  | 3.1 | Yes | Target | bar: P1 to Enter performance data in every yellow cell. P12
Achieved | bar: P1 to Enter performance data in every yellow cell. P12
| Number of patients with HIV Hep C co-infection receiving Hep C treatment |  |  | 3.2 | Yes | Target | P1: 70; P2: 110; P3: 150; Enter performance data in every yellow cell. P4: 35; Enter performance data in every yellow cell. P5: 70; Enter performance data in every yellow cell. P6: 110; Enter performance data in every yellow cell. P7: 150
[6 empty] | Achieved | P1: 60; P2: 72
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Number of MARPs (IDUs, MSM and FSWs) covered with HIV testing and counselling (including provision of results) |  |  | 1 | Yes | Target | 7720 | 6795 | 7503 | 5975.6615 | 5975.6615 | 6345.3885 | 6345.3885 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 9770 | 5975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number and percentage of MSM reached with HIV prevention programmes - defined package of services |  |  | 2.1 | Yes | Target | 945 | 680 | 748 | 990 | 990 | 1257.5 | 1257.5 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 346 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number and percentage of eligible adults and children currently receiving antiretroviral therapy |  |  | 3 | Yes | Target | 2330 | 2530 | 2740 | 3000 | 3000 | 3270 | 3270 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 2311 | 2410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on C108: Alexander Asatiani: Need conf.
Note on C111: Alexander Asatiani: Check
Menu

## Grant Detail
Dashboard: Georgia - HIV / AIDS
Country: | Georgia |  | Title of the Grant: |  | Sustaining and scaling up the existing national responses for implementation of effective HIV/AIDS prevention activities, improving survival rates of people with advanced HIV infection by strengthening treatment and care interventions
Component: | HIV / AIDS | Grant No. | GEO-H-NCDC | Start Date: |  | 2014-04-01 | Total Funding | 13771977
Round: | Round 10 | Phase: | Phase 2 | Principal Recipient: |  | NCDC
Report Period: | P2 | from: | 2014-07-01 | to: |  | 2014-09-30 | Latest Rating: | B1
Local Fund Agent: | UNOPS |  |  | Fund Portfolio Manager: |  | Tsovinar Sakanyan
Prepared by: | Alexander Asatiani |  |  | Report preparation date: |  | 2014-10-05
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Georgia - HIV / AIDS
Round 10 | Phase 2 |  |  |  | Report Period: |  | P2
Latest Rating: | B1 |  | NCDC |  | From: |  | 2014-07-01
|  | Sustaining and scaling up the existing national responses for implementation of effective HIV/AIDS prevention activities, improving survival rates of people with advanced HIV infection by strengthening treatment and care interventions |  |  |  | To: | 2014-09-30
Financial Indicators
F1: Budget and disbursements by Global Fund - in ($) Report Period: P2 |  |  |  | F3: Disbursements and expenditures - in ($) Report Period: P2
Comments: |  |  |  | Comments:
F2: Budget and actual expenditures by Grant Objective - in ($) Report Period: P2 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P2
Comments: | are they ready for implementation of objective 1 start in January |  |  | Comments:
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 45
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 0
|  |  |  | Days taken for disbursement to reach SRs |  | 5 | 3
Menu

## Management
Dashboard: Georgia - HIV / AIDS
Round 10 | Phase 2 |  |  |  |  | Report Period: |  | P2
Latest Rating: | B1 |  | NCDC |  |  | From: |  | 2014-07-01
|  | Sustaining and scaling up the existing national responses for implementation of effective HIV/AIDS prevention activities, improving survival rates of people with advanced HIV infection by strengthening treatment and care interventions |  |  |  |  | To: | 2014-09-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P2 |  |  |  | M2: Status of key PR management positions Report Period: P2
Comments: | The CP concerns the sustainablity plan: the budget is not signed yet |  |  | Comments: | Urgent need to select missing position to start objective 1 in Jan as planned
M3: Contractual arrangements (SRs) Report Period: P2 |  |  |  | M4: Number of complete reports received on time Report Period: P2
Comments: | New SR need to be selected to implement obj 1 |  |  | Comments:
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P2
Comments: |  |  |  | Comments: | Make sure the Government is ready to procure on its budget in 2015?
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Zidovudine/Lamivudine | 13.6704 | 6 | 7.6704
[5 empty] | Methadone (Tab.Mg) | 7.1744 | 3 | 4.1744
[5 empty] | Condoms (FSW) | 3.6056 | 3 | 0.60558
[5 empty] | Syringes (1ml) | 1.9741 | 3 | -1.0259
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Georgia - HIV / AIDS
Round 10 | Phase 2 | [7 empty] | Report Period: |  | P2
Latest Rating: | B1 |  | NCDC | [6 empty] | From: | 2014-07-01
|  | Sustaining and scaling up the existing national responses for implementation of effective HIV/AIDS prevention activities, improving survival rates of people with advanced HIV infection by strengthening treatment and care interventions | [7 empty] | To: | 2014-09-30 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of MARPs (IDUs, MSM and FSWs) covered with HIV testing and counselling (including provision of results) |  |  |  | Number and percentage of MSM reached with HIV prevention programmes - defined package of services |  |  |  | Number and percentage of eligible adults and children currently receiving antiretroviral therapy
Comment: P1 |  |  |  | Comment: P2 |  |  |  | Comment: P3
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of MARPs (IDUs, MSM and FSWs) covered with HIV testing and counselling (including provision of results) |  |  | 6795 | 5975 | 87.93% | [6 empty] | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number and percentage of MSM reached with HIV prevention programmes - defined package of services |  |  | 680 | 620 | 91.18% | [7 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number and percentage of eligible adults and children currently receiving antiretroviral therapy |  |  | 2530 | 2410 | 95.26% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of prisoners covered with VCT (HIV testing and counselling, including provision of results) |  |  | 1350 | 1311 | 97.11% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services |  |  | 1 | 1 | 100% |  |  | Based on the PF, this indicator will be reported on Feb 15, 2015. |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number and percentage of IDUs reached with HIV prevention programmes - defined package of services |  |  | 12500 | 1729 | 13.83% |  |  | This indicator will be changed shortly |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A
Number and percentage of FSWs reached with HIV prevention programmes - defined package of services |  |  | 650 | 714 | 109.8% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage of individuals receiving OST who received treatment for at least 6 months |  |  | 450 | 427 | 94.89% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage of adults and children that initiated ART, with an undetectable viral load at 12 months (<1000 copies/ml) |  |  | 1 | 1 | 100% |  |  | The indicator is be reported annually |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A
Number of patients with HIV Hep C co-infection receiving Hep C treatment |  |  | 110 | 72 | 65.45% |  |  | This is due to a low acceptance of the treatment by the patients |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Georgia - HIV / AIDS
Round 10 | Phase 2 |  |  |  |  | Report Period: | P2
Latest Rating: | B1 |  | NCDC |  |  | From: | 2014-07-01
|  |  | Sustaining and scaling up the existing national responses for implementation of effective HIV/AIDS prevention activities, improving survival rates of people with advanced HIV infection by strengthening treatment and care interventions |  |  | To: | 2014-09-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1
F2 |  | are they ready for implementation of objective 1 start in January |  |  | Follow up with PR regarding the preparation for objective 1
F3
F4
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | The CP concerns the sustainablity plan: the budget is not signed yet |  |  | Wait for budget approval by the paliament
M2 |  | Urgent need to select missing position to start objective 1 in Jan as planned | 1 | 0 | Follow up with PR regarding recruitment at the PR in preparation for objective 1
M3 |  | New SR need to be selected to implement obj 1 |  |  | Follow up with PR regarding SR selection process in preparation for objective 1
M4
M5
M6 |  | Make sure the Government is ready to procure on its budget in 2015? |  |  | For ministry to prepare the framework necessary for the national procurement of first line treatment to avoid stock out.
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend
P2 - trend
P3 - trend
P1
P2
P3
P4
P5 |  | Based on the PF, this indicator will be reported on Feb 15, 2015.
P6 |  | This indicator will be changed shortly
P7
P8
P9 |  | The indicator is be reported annually
P10 |  | This is due to a low acceptance of the treatment by the patients |  |  | Follow up with PR on how to improve the performance on this indicator
Menu

## Actions
Dashboard: Georgia - HIV / AIDS
| Round 10 | Phase 2 |  |  |  | Report Period: |  | P2
| Latest Rating: | B1 |  | NCDC |  | From: |  | 2014-07-01
|  |  | Sustaining and scaling up the existing national responses for implementation of effective HIV/AIDS prevention activities, improving survival rates of people with advanced HIV infection by strengthening treatment and care interventions |  |  |  | To: | 2014-09-30
Decisions and Actions
What is the overall status of this grant implementation?
After only 6 months of implementation the grant is already reaching its objectives. Preparation of objective 1 needs to be followed up and minitry needs to prepare to be able to procure treatment in 2015
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period | Follow up with PR regarding the preparations for objective 1 |  |  |  | The PR reports that there is no risk of delay for implementation of objective 1 | 28th of November | PR
| For ministry to prepare the framework necessary for the national procurement of first line treatment to avoid stock out. |  |  |  | Appointment of focal person within the MoH to prepare national procurement of first line drugs | January 15/2015 | MoH
| Follow up with PR on how to improve Hep C treatment indicator |  |  |  | Meeting with AIDS center and PR for consultation on this issue | 20th of Dec | OC David Ananiashvili
| Urgent appointment of a representant of the MoH within the OC |  |  |  | The ministry will appoint representant | 20th of Dec | MoH
| Urgent recruitment of the Executive Secretary |  |  |  | Selection and appointment of an appropriatecandidate for the position of the Executive Secertary for a probation period | As soon as possible. Preferably within one week after the CCM meeting | MoH
| Agreement of the CCM on the recommendation of the OC about the tranfer of remaining asset procured by former PR |  |  |  | The list of remaining assets will be sent and shall no reaction be gotten from CCM members the assets will remain at the GPIC | 15th of Dec | OC David Ananiashvili
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Georgia - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe