## 2016-2017 Work Plan
ANNUAL WORKPLAN March 2016-February 2017
Shaded cells (in green) indicate due periods.
[9 empty] | 2011 |  |  |  | March 2016-February 2017
Performance Area | Strategic Objective | Indicator | Q1 | Q2 | Q3 | Q4 | MoV | Activity | Oct | Nov | Dec | Category | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Comments | Status
1. Capacity Building | Enhanced knowladge and meaningful participation of CCM members and Secretariat in sustainable transition proccesses | % CCM members having followed a specific training on transition process |  |  |  | 90% | -CCM meeting MoM | 1.1 Regular update on PAAC activities at the CCM meetings |  |  |  | Meetings/trainings workshops
[8 empty] | 1.2. Orientation for new members |  |  |  | Meetings/trainings workshops
Activity
2. Constituency Engagement | Enhanced Engagement of Civil Society especially KAP and PLWD in transition processes | -at least 50 % of CCM members are actively involved in CSO forum - at least 50% of active CSO in TB and HIV field are actively engaged in CSO forum dedicated to transition process (planning and participation) |  |  |  | 50 % 50% | -ToR of the consultant -Signed contract with the consultant -Event participant list; -Event Photos, -MoM of the event | 2.1 Consultative meetings with CSO representatives to define main concept and topics of the event |  |  |  | Technical Assistance | bar: March 2016-February 2017 Oct
[8 empty] | 2.2 Agreement with the CCM on defined CSO event concept |  |  |  | Technical Assistance | bar: March 2016-February 2017 Oct
[8 empty] | 2.3 Recruitment of the consultants for facilitation CSO event |  | 2011-11-15 |  | Technical Assistance | bar: March 2016-February 2017 Oct to March 2016-February 2017 Nov
[8 empty] | 2.4 To conduct CSO forum |  |  |  | Meetings/trainings workshops | bar: March 2016-February 2017 Nov
[8 empty] | 2.5 Ensure media coverage of the event |  |  |  | Meetings/trainings workshops | bar: March 2016-February 2017 Nov
Activity
3. Constituency Engagement | Enhanced cooperation between all constituencies with internal and external partners and general public | -Communication plan is in place -Annual and quarterly bulletins are developed and placed on the website -Regular update of the CCM website | Yes | Yes | Yes | Yes | -Updated website -Communication Plan -quarterly and annual bulletins developed , placed on the website and printed as appropriate | 3.1 Production of quarterly and annual bulletins |  |  |  | Technical Assistance | bar: March 2016-February 2017 May; March 2016-February 2017 Aug; March 2016-February 2017 Nov; March 2016-February 2017 Feb
[8 empty] | 3.2 Placing of information produced by G-CCM on the CCM website as per specification of GM and communication plan |  |  |  | Technical Assistance
[8 empty] | 3.3. Opening and maintaining online platform for iteractive disussions on transition process (e.g facebook page) |  |  |  | Communication
Activity
4. Oversight | Proper oversight of GFATM grants is ensured | - no less than 6 CCM meetings conducted - no less than 4 site visits conducted - no less that 4 OC meetings held | 1 1 1 | 1 1 1 | 2 1 1 | 2 1 1 | -list of participants -meeting minutes | 4.1 CCM Meetings |  | 2011-11-15 |  | Planning and Administration | bar: March 2016-February 2017 Apr; March 2016-February 2017 Jun; March 2016-February 2017 Sep; March 2016-February 2017 Nov; March 2016-February 2017 Jan to March 2016-February 2017 Feb
[8 empty] | 4.2 Site Visits |  |  |  | Planning and Administration | bar: March 2016-February 2017 May; March 2016-February 2017 Aug; March 2016-February 2017 Nov; March 2016-February 2017 Feb
[8 empty] | 4.3 OC meetings |  |  |  | Planning and Administration | bar: March 2016-February 2017 Apr; March 2016-February 2017 Jul; March 2016-February 2017 Oct; March 2016-February 2017 Jan
Activity
5. Alignment | Smooth transition from GF to domestic funding with the support of PAAC* | -PAAC is established and functional -at least 4 meetings per year - the policy and advocacy framework for sustainable HIV/TB response is in place -CCM transformation plan is developed | 1 | 1 | 1 | 1 | -list of participants -meeting minutes -Policy and Advocacy framework document -CCM transformation plan | 5.1 Establishment of PAAC |  |  |  | Technical Assistance
5.2 Meeting of PAAC | bar: March 2016-February 2017 May; March 2016-February 2017 Jul; March 2016-February 2017 Sep; March 2016-February 2017 Dec
5.3 Elaborate the policy and advocacy framework for sustainable HIV/TB response | bar: March 2016-February 2017 Jun to March 2016-February 2017 Feb
5.4 Elaborate CCM transformation plan | bar: March 2016-February 2017 Jun to March 2016-February 2017 Feb
[8 empty] | 5.5. External expert review of technical deliverables developed by consutants/firms in support of the transition planning |  |  |  | Technical Assistance | bar: March 2016-February 2017 Feb
Activity
6. Alignment | Coordination of all on-going and up-coming innovative projects and clinical studies related to introduction of new TB treatment schemes | -TB clinical research coordination group is established and functional -CCM is regularly updated on planned and implemented clinical studies to ensure better coordination and harmonization | yes | yes | yes | yes | -'list of participants -meeting minutes | 6.1 Meeting of TB RCG |  |  |  | Technical Assistance | bar: March 2016-February 2017 Mar; March 2016-February 2017 Jun; March 2016-February 2017 Sep; March 2016-February 2017 Dec
* Policy and Advocacy Advisory Council

## 2017-2018 Work Plan
ANNUAL WORKPLAN March 2017-February 2018
Shaded cells (in green) indicate due periods.
[9 empty] | 2011 |  |  |  | March 2017-February 2018
Performance Area | Strategic Objective | Indicator | Q1 | Q2 | Q3 | Q4 | MoV | Activity | Oct | Nov | Dec | Category | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Comments | Status
1. Capacity Building | Enhanced knowladge and meaningful participation of CCM members and Secretariat in sustainable transition proccesses | % CCM members having followed a specific training on transition process |  |  | 90% | 90% | -CCM meeting MoM | 1.1 Regular update on PAAC activities at the CCM meetings |  |  |  | Meetings/trainings workshops
[8 empty] | 1.2 Orientation of new members |  |  |  | Meetings/trainings workshops
Activity
2. Constituency Engagement | Enhanced Engagement of Civil Society especially KAP and PLWD in transition processes | -at least 50 % of CCM members are actively involved in CSO forum - at least 50% of active CSO in TB and HIV field are actively engaged in CSO forum dedicated to transition process (planning and participation) |  |  |  | 50 % 50% | -ToR of the consultant -Signed contract with the consultant -Event participant list; -Event Photos, -MoM of the event | 2.1 Consultative meetings with CSO representatives to define main concept of the event |  |  |  | Technical Assistance | bar: March 2017-February 2018 Oct
[8 empty] | 2.2 Agreement with the CCM on defined CSO event concept |  |  |  | Technical Assistance | bar: March 2017-February 2018 Oct
[8 empty] | 2.3 Recruitment of the consultants for facilitation CSO event |  | 2011-11-15 |  | Technical Assistance | bar: March 2017-February 2018 Oct to March 2017-February 2018 Nov
[8 empty] | 2.4 To conduct CSO forum |  |  |  | Meetings/trainings workshops | bar: March 2017-February 2018 Nov
[8 empty] | 2.5 Ensure media coverage of the event |  |  |  | Meetings/trainings workshops | bar: March 2017-February 2018 Nov
Activity
3. Constituency Engagement | Enhanced cooperation between all constituencies with internal and external partners and general public | -Communication plan is in place -Annual and quarterly bulletins are developed and placed on the website -Regular update of the CCM website | Yes | Yes | Yes | Yes | -Updated website -Communication Plan -quarterly and annual bulletins developed , placed on the website and printed as appropriate | 3.1 Production of quarterly and annual bulletins |  |  |  | Technical Assistance | bar: March 2017-February 2018 May; March 2017-February 2018 Aug; March 2017-February 2018 Nov; March 2017-February 2018 Feb
[8 empty] | 3.2 Placing of information produced by G-CCM on the CCM website as per specification of GM and communication plan |  |  |  | Technical Assistance
[8 empty] | 3.3. Maintaining online platform for iteractive disussions on transition process (e.g facebook page) |  |  |  | Communication
Activity
4. Oversight | Proper oversight of GFATM grants is ensured | -no less than 6 CCM meeting - no less than 4 site visits - no less that 4 OC meetings | 1 1 1 | 1 1 1 | 2 1 1 | 2 1 1 | list of participants meeting minutes | 4.1 CCM Meetings |  | 2011-11-15 |  | Planning and Administration | bar: March 2017-February 2018 Apr; March 2017-February 2018 Jun; March 2017-February 2018 Sep; March 2017-February 2018 Nov; March 2017-February 2018 Jan to March 2017-February 2018 Feb
[8 empty] | 4.2 Site Visits |  |  |  | Planning and Administration | bar: March 2017-February 2018 May; March 2017-February 2018 Aug; March 2017-February 2018 Nov; March 2017-February 2018 Feb
[8 empty] | 4.3 OC meetings |  |  |  | Planning and Administration | bar: March 2017-February 2018 Apr; March 2017-February 2018 Jul; March 2017-February 2018 Oct; March 2017-February 2018 Jan
Activity
5. Alignment | Smooth transition from GF to domestic funding with the support of PAAC | PAAC is established and functional draft of the transitional plan is in place at least 4 meetings per year | 1 | 1 | 1 | 1 | list of participants -meeting minutes -Results of external review | 5.1 Meeting of PAAC |  |  |  | Technical Assistance | bar: March 2017-February 2018 Mar; March 2017-February 2018 Jun; March 2017-February 2018 Sep; March 2017-February 2018 Dec
5.2. External expert review of technical deliverables developed by consulltants/firms in support of the transition planning | bar: March 2017-February 2018 Mar to March 2017-February 2018 Aug
Activity
6. Alignment | Coordination of all on-going and up-coming innovative projects and clinical studies related to introduction of new TB treatment schemes | TB clinical research coordination group is established and functional CCM is regularly updated on planned and implemented clinical studies to ensure better coordination and harmonization | yes | yes | yes | yes | list of participants meeting minutes | 6.1 Meeting of TB RCG |  |  |  | Technical Assistance | bar: March 2017-February 2018 Mar; March 2017-February 2018 Jun; March 2017-February 2018 Sep; March 2017-February 2018 Dec