## Cover Sheet
On-going Progress Update and Disbursement Request and LFA On-going Progress Review and Disbursement Recommendation
In completing this report, please refer to the detailed "Guidelines for completing the PR “ongoing progress update and disbursement request”, and LFA “ongoing progress review and disbursement recommendation”
During the lifetime of a grant, the Global Fund periodically disburses funds to the Principal Recipient (PR) based on demonstrated program performance and financial needs for the following period of implementation. The PR’s ongoing progress update and disbursement request (PU/DR) is both a progress report on the latest completed period of program implementation and a request for funds for the following period of implementation. Its purpose is to provide an update of the programmatic and financial progress of a Global Fund-financed grant, as well as an update on fulfillment of conditions precedent, management actions and other requirements. The PU/DR, alongside the Local Fund Agent (LFA) ongoing progress review and disbursement recommendation (short-form: LFA-verified PU/DR), forms the basis for the Global Fund’s disbursement decision by linking historical and expected program performance with the level of financing to be provided to the PR. One Excel file contains both the PR’s PU/DR and the LFA-verified PU/DR. The PR should only complete the worksheets of the file pertaining to the PU/DR (the worksheet tabs color-coded in green), whereas the LFA should complete the worksheets of the file pertaining to the LFA-verified PU/DR (the worksheet tabs color-coded in blue). The Excel file also includes a reference checklist of supporting documents for the PU/DR review (the worksheet tab color-coded in yellow). This checklist is included for information and not for completion. The PU/DR should be completed by the PR of a Global Fund grant for every period in which a progress update is required, usually either on a quarterly, semiannual or annual basis, regardless of whether or not a disbursement is being requested. Once a year, the PR is expected to submit the Enhanced Financial Report (EFR) as part of the PU/DR (there is a dedicated tab for EFR in the Excel file). The PR is required to submit the PU/DR to the LFA within 45 calendar days from the closing date of the relevant progress update period when the report does not contain the EFR (as indicated in the performance framework of Annex A of the grant agreement) and within 60 calendar days when the report contains the EFR (once a year). The LFA should complete and submit a signed copy of the LFA-verified PU/DR to the Global Fund within ten working days after receiving the final signed version of the PU/DR from the PR and within 13 working days when the PU/DR report contains the EFR (once a year), unless agreed otherwise with the FPM (The LFA does not need to submit original/hard copies of each PU/DR reports. However, these documents should be available at the LFA’s offices for any audit/reviews. Also, the LFA should be ready at all times to submit these originals to the Secretariat upon request). In this report the LFA should provide an analysis and comments based on verification of the PR-reported information, document grant risks and recommendations for improving program implementation, and finally, provide a performance rating to the grant and disbursement recommendation for the Global Fund’s consideration. In defining the performance rating and recommending a disbursement amount, the LFA should use the Grant Rating Methodology of the Global Fund (as described in Annex 2 and communicated at various regional meetings and LFA training events) along with the Excel version of the Grant Rating Tool (to be provided to LFAs) to support the calculation of Indicator Rating.
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Programmatic Progress_1A
On-going Progress Update and Disbursement Request | [13 empty] | Select
AIS (AIDS Indicator Survey)
BSS (Behavioral and Surveillance Survey)
GENERAL GRANT INFORMATION | [13 empty] | Census
Country: |  | Georgia | [11 empty] | Clinical cohort follow-up studies
Disease: |  | HIV/AIDS | [11 empty] | DHS/DHS+ (Demographic and Health Survey)
Grant Number: |  | GEO-H-NCDC | [11 empty] | MICS (Multiple Indicator Cluster Survey)
Principal Recipient: |  | NCDC | [11 empty] | MIS (Malaria Indicator Survey)
Program Start Date: |  | 2014-04-01 | [11 empty] | WHO Global report/estimates
Currency: |  | EUR | [11 empty] | Other (type as appropriate)
PROGRESS UPDATE
Progress Update - Reporting Period: |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 2
DISBURSEMENT REQUEST
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2015-01-01 | End Date: | 2015-12-31
Disbursement Request - Number: |  | 2
Section 1: Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Year of Target | Intended Target | Report Due Date | Actual Result | Data Source of Results | Comments on results on Impact/Outcome indicators and data sources, and any other comments
[6 empty] | Value | Year
Impact | Percentage of men who have sex with men who are living with HIV |  |  |  |  | 13 | 2012 | 2015 | 1500% | 2016-02-15 | n/a | BSS (Behavioral and Surveillance Survey) | Based on the PF, this indicator will be reported on Feb 15, 2016.
Impact | Percentage of people who inject drugs who are living with HIV |  |  |  |  | 3 | 2012 | 2014 | 300% | 2015-02-15 | n/a | BSS (Behavioral and Surveillance Survey) | The BSS was postponed and the results will be avilable in May,2015; however, the preliminary data will be available by the submission of CN for HIV component
Impact | Percentage of sex workers who are living with HIV |  |  |  |  | 1.1 | 2012 | 2014 | 230% | 2015-02-15 | 0.7% | BSS (Behavioral and Surveillance Survey) | The prevalcne of HIV in Tbilisi was 0.6% and 0.8% in Batumi, total number of study participants tested on HIV was 277
Impact | AIDS related mortality per 100,000 population |  |  |  |  | 2.4 | 2012 | 2014 | 230% | 2015-02-15 | 210% | HMIS
Outcome | Percentage of adults and children with HIV known to be on treatment 12 months after initiation of antiretroviral therapy. |  |  |  |  | 0.85 | 2013 | HMIS | 86% | 2016-02-15 | 87% | HMIS
Outcome | Percentage of men reporting the use of a condom the last time they had anal sex with a male partner |  |  |  |  | 0.673 | 2012 | BSS (Behavioral Surveillance Survey) | 75% | 2016-02-15 | n/a | BSS (Behavioral and Surveillance Survey) | Based on the PF, this indicator will be reported on Feb 15, 2016.
Outcome | Percentage of sex workers reporting the use of a condom with their most recent client |  |  |  |  | 91.1% | 2012 | BSS (Behavioral Surveillance Survey) | 92% | 2015-02-15 | 90% | BSS (Behavioral and Surveillance Survey) | The value of the indicator was 94.4% in Tbilisi, but it was only 82.7% in Batumi (total number of respondents was 224
Outcome | Percentage of people who inject drugs reporting the use of sterile injecting equipment the last time they injected |  |  |  |  | 83.5% | 2012 | BSS (Behavioral Surveillance Survey) | 84% | 2015-02-15 | n/a | BSS (Behavioral and Surveillance Survey) | The BSS was postponed and the results will be avilable in May,2015; the date of submission is agreed with GF; However, the preliminary data will be available before submission of CN for HIV component
Select | [5 empty] | - | - | - | - | - | - | Select
Select | [5 empty] | - | - | - | - | - | - | Select

## PR_Programmatic Progress_1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  |  | GEO-H-NCDC
Progress Update - Reporting Period: |  |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  |  | 2
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators
Objective No. | * Indicator No. | Indicator Description |  |  |  | Tied To | Targets cumulative? | Top 10 indicator? | Baseline (if applicable) |  | Intended Target to date | Actual Result to date | % achievement (Please calculate as appropriate) | Reasons for programmatic deviation from intended target and deviations from the related workplan activities
[9 empty] | Value | Year
2 | 1 | Number of MARPs (IDUs, MSM and FSWs) covered with HIV testing and counselling (including provision of results) |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 9296 | 2013 | 14298 | 12637 | 88.38% | Number of PWIDs reached with VCT services during P2 is 11243 (11243/12620 - 89%); Number of MSM who recieved VCT is 712 (712/1003=71%) and number of FSWs is 682 (682/675=101%) The overachivement is partially resulted from hiring additional staff (mobile ambulatory personnel for NST program) for outreach work that increased covereadge of PWIDs with VCT service (source for the data is electronic dabatase of SRs - GHRN and Tanadgoma)
2 | 1.1. | Number of prisoners covered with VCT (HIV testing and counselling, including provision of results) |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 1938 | 2013 | 2850 | 2388 | 83.79% | Mainly the underachivement is a result of dicreased total number of inmates (10,000 vs. 24000). Starting of the HCV treatment Program in penitentiary system erly 2014 has increased interest in VCT among prisoners. We untisipate that the same trend will remain. (source is electronic dabase of SR - Tanadgoma)
2 | 1.2 | Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 87.7% (430/490) | 2013 | 89% | 91.1% | 102.4%
2 | 2.1 | Number and percentage of MSM reached with HIV prevention programmes - defined package of services |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 4.5% (765/17000) | 2013 | 8% (1428/17000) | 6.4%(1087/17000) | 76.1% | The changes in the system of counting the coverage of the key affected populations has allowed the SRs to report increased coverage. Hiring of additional staff for outreach work especially affected the coverage of PWIDs with HIV prevention package. Coverage of FSWs and MSM was considerably increased compared to P1 but still needs additional efforts. New intervention - PDI, that was tested among MSM turned out to be successful also (source for the data is electronic dabatase of SRs - GHRN and Tanadgoma)
2 | 2.2 | Number and percentage of IDUs reached with HIV prevention programmes - defined package of services |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 36% (16208/45000) | 2013 | 40% (17925/45000) | 57% (25838/45000) | 144.1%
2 | 2.3 | Number and percentage of FSWs reached with HIV prevention programmes - defined package of services |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 9.7% (776/8000) | 2013 | 19% (1232/6500) | 16.1% (1044/6500) | 84.7%
2 | 2.4 | Percentage of individuals receiving OST who received treatment for at least 6 months |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 16% (400/2450) | 2013 | 450 | 503 | 111.8% | 503 people were receiving OST through GF funding continuously over the period of 6 months
2 | 2.5 | Percentage of key affected population screened for TB |  |  |  | Current grant | N-not cumulative | No | N/A |  | 40% (3002/7503) | 36% (2673/7503) | 89.04% | Although, the indicators and the activity is relatively new for HIV Program, the good results were achieved by SRs. 2472 PWIDs and 118 FSWs and 83 MSM were screened on TB during October-December, 2014 (Source is electronic database of GNRH and Tanadgoma).
3 | 3 | Number and percentage of eligible adults and children currently receiving antiretroviral therapy |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 51.5%(2092/4060) | 2013 | 60.0%(2740/4570) | 55% (2590/4570) | 94.5% | 2590 patients were receiving ART as of December 31, 2014. The underachivement is a result of lower HIV detection rate than it was initially projected. Coverage of already detected HIV patients with monitoring investigations for eligibility for ART still remains high (indicator 1.2.) (Source is electronic database of National AIDS Center)
3 | 3.1 | Percentage of adults and children that initiated ART, with an undetectable viral load at 12 months (<1000 copies/ml) |  |  |  | Current grant | Y-cumulative annually | No | 83% (101/121) | 2013 | 83% | 81.5% | 98.2% | The achivement is a result of close monitoring of patients on ART, including follow ups with mobile ART monitoring units. (Source is electronic database of National AIDS Center).
3 | 3.2 | Number of patients with HIV Hep C co-infection receiving Hep C treatment |  |  |  | Current grant | Y-cumulative annually | No | 152 | 2013 | 150 | 136 | 90.67% | Underachivement partially is a result of delay in procurement of pegilatied interrfern (National AIDS Center was cortoling the stock for current patients and was reluctant to enroll new patients in the program). As soon as the medicine was provided, they accelerated the enrollment of eligible patients in the program. Although, some of them are refusing to get interferon treatment due to the state anouncement regarding of starting the free treatment with more effective medicine - Sofosbovir in 2015.
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
* Indicator No. should correspond to the indicator number listed in the approved Performance Framework of the grant (1.1, 1.2, etc.)
C. Analysis of data quality and reporting issues (!) This section should contain (1) a summary of issues related to data quality and reporting on programmatic indicators, and any relevant issues which are not covered in 'Reasons for programmatic deviation', and (2) remedial actions that are underway or planned to address these issues.

## PR_Grant Management_2
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | GEO-H-NCDC
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: | 2
Section 2: Grant Management
A. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! Please include in this table the CP number as per Grant Agreement and full text of CPs and/or other special conditions due for fulfilment during this period or outstanding from previous periods. ! Some Special Conditions may apply to more than one period of grant implementation. Their fulfilment during one period does not automatically imply fulfilment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
Conditions Precedent and/or other special conditions |  |  | Status | PR Comments on Progress of Implementation
1. Conditions Precedent to the First Disbursement (Terminal Date as stated in block 7A of the Face Sheet): The first disbursement of Grant funds by the Global Fund to the Principal Recipient is subject to: a) the Principal Recipient entering into temporary arrangements with the existing Sub- recipients carrying out Program activities, under grant number GEO-H-GPIC, until the Principal Recipient submits a request for tender in accordance with the laws of Georgia, and new Sub-recipients are selected through such tender (for the avoidance of doubt, during such temporary arrangements period, the Standard Terms and Conditions of this Agreement shall apply); |  |  | Met
The first disbursement of Grant funds by the Global Fund to the Principal Recipient is subject to: b) delivery by the Principal Recipient to the Global Fund, in form and substance satisfactory to the Global Fund, of a letter signed by the Authorized Representative of the Principal Recipient setting forth the name, title and authenticated specimen signature of each person authorized to sign disbursement requests under Article 10 of the Standard Terms and Conditions of this Agreement and, in the event a disbursement request may be signed by more than one person, the conditions under which each may sign. |  |  | Met
2. Condition Precedent to the Use of Grant Funds by the Principal Recipient for procurement of health and non-health products (Terminal Date as stated in block 7B of the Face Sheet): The use of Grant funds by the Principal Recipient for procurement of health and non-health products is subject to delivery by the Principal Recipient to the Global Fund, each in form and substance satisfactory to the Global Fund, of an Operations Manual (OM) which shall include procedures in respect of Procurement and Supply Management and regular progress updates, and shall address weaknesses identified by the Principal Recipient assessment, including but not limited to the following: a) Standard Operating Procedures (SOPs) for procurement of health and non-health products; and b) SOPs for supply chain management (including management information systems, forecasting and quantification, storage and distribution) of health products and pharmaceuticals on a national level (from central level to patient level). Notwithstanding the foregoing set forth in this Section B(2)(b), prior to the satisfaction of this condition precedent, the Principal Recipient may use Grant funds, with the prior written approval of the Global Fund, for procurement of non-health products. |  |  | Met
3. Conditions Precedent to disbursement by the Global Fund to the Principal Recipient or use by the Principal Recipient of Grant funds to finance activities related to Objective 1: The Global Fund and the Principal Recipient shall agree on the list of activities related to Objective 1 | Select |  | Met
4. Condition Precedent to disbursement by the Global Fund to the Principal Recipient or use by the Principal Recipient of Grant funds for the 2015 budget: a) No later than 14 August 2014, the Ministry of Labour, Health and Social Affairs shall inform the Global Fund of the HIV treatment protocol that will be used in Georgia during the current implementation period; upon which the Global Fund will determine its ART funding contribution which would be incorporated into the 2015 budget (the Global Fund reserves a right to limit the ART funding to the treatment regimens recommended in the WHO 2013 treatment guidelines). |  |  | Met
4. Condition Precedent to disbursement by the Global Fund to the Principal Recipient or use by the Principal Recipient of Grant funds for the 2015 budget: b) By no later than 30 September 2014, revision by the Principal Recipient of the 2015 budget and Performance Framework targets for key populations, which shall further optimize and incorporate the results of: i) the population size estimates conducted between 1 January to 31 July 2014. and; ii) the Budgeted Sustainability Plan pursuant to Section C(2) of this Annex A (June 30, 2014) The date was postponed by GF with IL1 to 31,January,2015. |  |  | Met | In December, 2014 the Parliament of Georgia has approved the state budget law for 2015, the cost for first line ARV medicines in the amount of 1,700,000 GEL is included in the State Budget. The updated National Strategic Plan will contain program sustainability plan as it will indicate the relevant funding sources for the specific activities. The NSP will have high mandate as it will be submitted to the Camibet of Ministers for approval.
SPECIAL TERMS AND CONDITIONS FOR THIS AGREEMENT No later than 30 June 2014, the CCM shall, or the Principal Recipient shall cause the CCM to, submit a Budgeted Sustainability Plan for the gradual governmental take-over of financing, starting in 2015, for activities supported by this Grant. GF agreed to postpone the terminal date of the condition to 31 January, 2015 | Select |  | Met | See the coment above
At its sole discretion, the Global Fund reserves the right to require the principal recipient to use the services of a suitability qualified procurement agent for the procurement of designated list of health products, including pharmaceuticals, for reasons of quality, and or value for money. when invoking this right, the Global Fund will stipulate the list of health products |  |  | Met | Relevant PQ-s are signed with VPP and IDA for procurement of ARV medicines (adults and pediatric drugs) and condoms; the PQ regarding the syringes is under final review and will be signed early March, 2015. The negotiation for 1ml syringe took much time as IDA couldn't timely find company that would supply with syringes of desired specifications.
Select
Select
Select
Select
Select
Select
B. PR REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! Please list all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress. Please include the date of the management letter and the item number.
Global Fund Management Actions |  | PR Comments on Progress of Implementation
Financial management and systems During revision of the Work plan and Budget it has been noted that the PR tends to modify the budget under negotiation on ongoing basis. This practice has created a confusion, as there was a difference in multiple versions submitted to the Secretariat. Additionally it has resulted in CT's considerable time for verification, clarifications, and unnecessary communication. Action Required: The budget approved by the Global Fund should be treated as a plan, and should not be changed on an ongoing basis. The re-programming requests should be approved by Global Fund through the official request, and variance between the originally approved budget and re-allocations should be reported as part of the EFR |  | The request is fully noted. All future reprogramming actions will be sent to GF for official approval with relevant re-allocation requests. The variances for P1 and P2 period budget allocations are reported in current EFR.
Qpioid Substitution Program While the overall achievement of the OST indicator does not raise questions, our further discussions have revealed that OST patients are transferred from the State Program to the GF Program by the State Program officials due to inability of patients to cover the co-payment requested by the state program or difficulties to manage patients with some mental problems. Since the movements of the patients are controlled by the State Program, and currently free treatment is provided by the Global Fund, the move of the patients to the Global 'Fund program for the above mentioned reasons is understandable. However, it raises an ethical issue of continuation of the treatment for the most disadvantaged group, when the Global Fund discontinues the OST activities in Georgia. In view of the above, we strongly recommend that the PR causes the CCM, as part of the sustainability plan, to initiate discussions on the future adoption of the co-payment waver policy for disadvantaged OST patients, or find any other appropriate solutions, for gradual inclusion of the GF program OST patients into the state program. |  | The discussion regarding the future funding needs of OST programs supported from the GF grant was initiated at the last CCM meeting on January 30, 2015. Minister Davit Sergeenko will organize a follow up meetings with relevant stakeholders (State OST Program Management group) to find relevant solutions. Although, since 2015 the Mental Health and Addiction Prevention Center is responsible for implementation of both, the state and GF supported OST Programs that will make the transfer of patients from one program to another easier. Number of HIV positive patients enrolled into GF OST programs is not large (29) and shouldn’t be difficult to accommodate their needs within the state program. In addition, patients whose social vulnerability score is below 70,000 are eligible for state program full coverage. Tbilisi municipality is planning to cover cost of those OST program patients whose score is between 70,000 and 150,000 which will be a considerable support for OST patients living in and around Tbilisi.
Issue: During the review, it was noted that the SRs have experienced stock outs in condoms, lubricants due to the late procurement by the previous PRoFurthermore, the Global Fund Secretariat is aware of the complexity of the regulations and the processes of the State Procurement Agency, which may potentially result in delayed procurement of drugs and stock outs. Action required: The PR should continue to update the Global Fund on the progress made with respect to the procurement of drugs and health products and to continue to monitor the process. While the Global Fund Secretariat acknowledges the efforts made by the PR to streamline the processes, the PR is requested to continue to follow up and ensure that the orders are placed in timely manner and the buffer period is included in the calculations, in order to avoid stock out of medicines and health products and interruption of services. |  | The procurement process was much accelerated during the P2. All key health products and medicines were procured and provided to SRs. There is still delay in procurement of mobile ambulatories, office furniture, office equipment and some minor laboratory supplies, that will be conducted during Q1 of 2015. The experience gained during the P2 will considerable simplify the procurement processes during in 2015 as the PR is planning to procure mostly the same items.
During the PHPM review of the TB and HIV Grants conducted in July 2014, the Global Fund has provided set of recommendations on the issues identified in 27 sites. The PR submitted a consolidated feedback on 11h of October 2014 including proposed measures to address the issues identified as well as updated the Global Fund on the progress made with respect to completion and implementation of the Maintenance and Service Plan for health procurement under the Global Fund grants. We appreciate the PR's efforts so far. Please be informed that we will be conducting a follow up mission to review the progress on the implementation of the Maintenance and Service Plan. |  | The latest update regarding the PSM improvement plan implementation was requested from SRs on January 15th, 2015 and SRs have provided the current statuses. The PR has developed the second letter based on the status updates provided by SRs to reinforce the implementation of the plan and will continue the monitoring as on-going process. The letter will be sent early March with relevant reporting documents
We recognize that the PIU has been established several months ago, and the staff needs sufficient time to learn and adapt to the requirements of the Global Fund. However, taking into consideration the capacity building opportunities provided by the GF and GMS, it is expected that less iterations should take place for the key grant documents (revised Budget and Work plan, PSM related documents, and Performance Framework) prepared by the PRoWe do hope to see more progress in the future. |  | The PR acknowledges this responsibility. The current key grant documents are harmonized and PR doesn't anticipate any major revisions that may require intensive communication with GF.
C. PR COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
! Please indicate a date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
Required Documentation |  | Due date (dd-mmm-yy) | Status | Comments
PR Audit Report |  | 2015-03-31 | Select | The audit service is procured from KPMG Georgia and report will be provided according to the schedule.
Enhanced Financial Reporting (EFR) |  | 2015-02-28 | Select | EFR is submitted along with PU/DR within the deadline set by GF.

## PR_Total PR Cash Outflow_3A
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | GEO-H-NCDC
Progress Update - Reporting Period: |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 2
Currency: |  | EUR
Section 3A: Total PR Cash Outflow
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
1. Total PR cash outflow vs. budget | 3370173.8693 | 2752053.64 | 618120.2293 |  |  | 6365135.8508 | 3127372.9291 | 3237762.9217
1a. PR's total expenditures | 1512380.6546 | 990032.05 | 522348.6046 | 5) Net variance of EUR 522,349 consists of Positive variance of Euro 1,252,306 and negative variance of Euro 729,957 Positive variance is derived from activities that were budgeted in current reporting period and represents either saving or postponed activity. Euro 959 - There was saving in procuring disinfectants due to Available stock at Sr Euro 1,296 - Actual printing costs For SRs occured to be less than budgeted Euro 624- Actual unit cost for computers provided to Srs were less than budgeted Euro 35,208 - Saving in Fuel cost derived from: a) Actual unit price less than budgeted b) available fuel vouchers provided by the previous PR. Euro 229,154 – Saving in ARVs resulted from actual PQ signed with PPM (lower unit costs were offered and PSM cost was also less than budgeted); Saving: Euro 8,576 – Saving in pharmaceuticals is caused by cheaper unit price for local procurement. Euro 30,212 - Actual Project management costs were less than budgeted including late recruitment of staff members (HIV M&E specialist salary and logistics specialist ) ; fuel; tender announcement costs, Technical assistance; late start of media campaign and etc. Euro 10,000 was saved in Quality control of ARVs (will be implemented within 2015 with relevant amount budgeted in 2015); Postponed activities: Euro 890,702 - Disbursement for Arvs due to the change in the payment method (payment after delivery) Euro 10,757 - Procurement of Tests and lab supplies for objective 4 was included into the service contract with SR CIF (agreed with GF, ref - email of August 5, 2014 ) and will be reimburced in 2015 according to the respective contract with SR. Euro 14,773 – Development of database (unified database for all SRs working on HIV prevention among key population groups (PWIDs, FSWs and MSM) was delayed. Euro 14,355- Project management cost for ERP system extension; Fire system installation and trainigs were postponed to the next period. Commitments: Euro 5,690 - fuel (both for PR and Srs) and PR GSM service cost for December reimbursed in January 2015 Negative Variance: Euro 729,957 – Actual cost of all procurements that were delayed from Q2 budget (HPHE; computers; printing materials and etc.) Absorption rate: 65,5% |  | 3553454.3749 | 1006122.6851 | 2547331.6898 | 1) Net variance of Euro 2,547,332 consists of positive (Euro 2,567,240) and Negative (Euro 19,908) Variances: Positive Variance: Savings: Euro 868,262 - There was saving in procuring health products and equipment due to the following factors: 1. Local procurement with competitive bidding with preceding market assessment derived cheaper unit costs compared to the budgeted amounts; 2. Available stocks at SR and Re-calculation of average consumption rates; Euro 31,940 - Actual printing costs occured to be less than budgeted Euro 2,987- Actual unit cost for computers provided to Srs were less than budgeted (computers were procured through consolidated tender conducted by state procurement agency and lower price was achieved) Euro 79,588 – Saving in pharmaceuticals consists of : a) Volume of methadone reduced based on the quota of methadone for the country, remaining amount agreed with the Drug Regulation Agency will be procured in 2015 within 2015 budget; b) Some drugs not procured due to the avaliable stock at SR ; c) Cheaper unit price has resulted from local procurement Euro 47,881 - Saving in Fuel cost derived from: a) Actual unit price less than budgeted (fuel was procured through consolidated tender conducted by state procurement agency) b) available fuel vouchers provided by the previous PR. Euro 229,154 –Saving in ARVs resulted from actual PQ signed with PPM (lower unit costs were offered and PSM cost was also less than budgeted); Euro 62,960 - Actual Project management costs were less than budgeted including late recruitment of staff members (HIV M&E specialist and logistics specialist ) ; saving related to renovation of office; procuring furniture (It was handed over from previous PR) ; fuel; tender announcement costs, Technical assistance; late start of media campaign. Euro 10,000 was saved in Quality control of ARVs (will be implemented within 2015 with relevant amount budgeted in 2015); Euro 57,220 - cancelled activities are as follows: Procurement of vehicles for SRs , refurbishment of new ART center in Telavi; Database upgrade for Aids Center is included in the SR contract. Postponed activities: Eur 890,702 - Disbursement for ARVs due to the change in the payment method (payment upon delivery) Euro 556 – Emergency amount of STA medicines was procured as tender failed two times, procurement of the remaining amount was postponed to the next period. Euro 184,865 - Procurement of health products and equipment including IDA order for syringes and Mobile Laboratories were postponed. The first tender for mobile labs failed and a new one was alreday anounced and contract will be signed in March, 2015. Euro 28,860 - Procurement of Tests and lab supplies for objective 4 was included into the service contract with SR CIF (agreed with GF, ref - email of August 5, 2014 ) and will be reimburced in 2015 according to the respective contract with SR. Euro 14,773 – Development of database (instead of GHRN database PR has decided to develop unified database for all SRs working on HIV prevention among key population groups (PWIDs, FSWs and MSM) was postponed. Currently, procurement is initiated and contract signing is anticipated in April, 2015. Euro 29,767- Procurement of office furniture/equipment for SRs was postponed, the procurement has been initiated and the contract will be signed by the end of March, 2015. Repairment of new OST center was re-planned for 2015 due to pending decision regarding the location and finding relevant space. Euro 32,035- Project management cost for ERP system extension; Several consultations took place with GF, LFA, State Treasury, HSSP project technical staff, previous PR. The issue is communicated with multiparty involvement. Partners’ consensus is needed for final technical and functional solutions. Fire system installation and trainigs were postponed to the next period. Commitments: Euro 5,690 - fuel (both for PR and Srs) and PR GSM service cost for December reimbursed in January 2015 Negative Variance: Euro 19,908 - Actual unit cost for some lab supplies occured slightly greater than budgeted (Supplies / consumables for HIVDR;Chlamydia immunofluorescence DFA KIT) Absorption rate: 28,3%
1b. Disbursements to sub-recipients | 1857793.2147 | 1762021.59 | 95771.6247 | 6) The reporting period relates activities performed by the SRs for July-December period. Within the current reporting period SRs received payment for June-November (GHRN in addition received reimbursement for April-May) and Advance payments (TG&HAPS) to be used for total contract period received. Total reimbursement for services equal EUR 1,729,843 ( TG- EUR 205,250; HAPS –EUR 70,529 ; MHDAC –EUR 295,095; Aids Center EUR 321,394; CIF –EUR 78,406, GHRN- EUR 759,170) and Advance Payments TG-EUR 27,807; HAPS – EUR 4,371. The variance consists of a) differences between periods for which SRs were reimbursed and the budget periods b) savings in program implementation (less amounts were spent per activities) Absorption rate : 95% |  | 2811681.4759 | 2121250.244 | 690431.2319 | Savings: Euro 198,790 – Savings in HR and ME costs is resulted from several reasons: a) delay in procurement of mobile ambulatories and hiring relevant personnel, in addition the cost of case management and reimbursements for medical consultations that PWID actually received was less than budgeted as the cost is related to actual demanded for these services. b) Hiring of planned additional personnel for ART treatment centers (relevant professionals with required qualification were not found) and cancelled opening of new ART regional center in Telavi (The need was re-evaluated based on the number of PLHIV living in Kakheti region) c) opening of new OST center and hiring of the Center's personnel (pending decision regarding the location and space allocation) d) BSS among IDUs started in October 2014 but field work was started with slight delay and the part of cost for interviewers was saved. Euro 14,503 Actual vehicle/office equipment maintenance costs were less than budgeted; Euro 1,993 – Savings in development of IEC materials; Euro 35,927– PDI incentives were not fully utilized; Procurement of milk formula for newborns of HIV positive mothers by AIDS Center failed and limited amount was procured; actual spending on medical investigations of PLHIV was less than budgeted; Euro 77,187– Actual cost for utilities, rent; office supplies and stationary were less than budgeted; Euro 61,669 – Actual cost for trainings and technical assistance (round table meetings; conferences; staff meetings) was less than budgeted: Euro 1115 – saving in Essential drugs procured by Aids Center Postponed: Euro 54,612 – Implementation of Objective 1 was delayed (budget was approved on July 30, 2014) due to requirement to get agreement from Ministry of Health and change the procurement plan accordingly, followed by market search and preparation of tender documentation. Some of the contracts for Objective 1 are signed (strengthening of LGBT community, strengthening of HIV community, Advocacy component, training of HCWs), others will be completed by end of March. Euro 6,573 –CIF – delay in reimbursement for testing of blood samples for IDU BSS and hiring of data entry personnel was postponed by Aids Center Eur 11,000 -Training of personnel on overdose was postponed by GHRN. Overspending: Euro 2,043 - Advanced from 1Q2015 budget (GHRN Euro 1,147 transportation costs; CIF – Euro 896 local consultant reimbursement) Euro 2393 - The amount was reallocated by CIF from HR as a part of tender proposal Euro 3433 – change in category by MHDAC (training was put ME and OVE was moved to PSM) Absorption rate : 75%
| Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
2. Total pharmaceutical & health product expenditures vs. budget | 1051878.3797 | 842595.3534 | 209283.0263 |  |  | 2883695.7433 | 842595.3534 | 2041100.3899
2a. Medicines and pharmaceutical products | 1040162.365 | 169300.0424 | 870862.3226 | The expenditure relates to the Medicines and Pharmaceuticals procured locally and directly by The Global Fund. The variance is due to several reasons: Saving: Euro 8,576 – Saving in pharmaceuticals is caused by cheaper unit price for local procurement. Euro 93,811 – Saving in ARVs resulted from actual PQ signed with PPM (lower unit costs were offered and PSM cost was also less than budgeted); Postponed: Eur 805,451 -Procurement of ARVs due to the change in the payment method (payment after delivery) Euro 556 – Emergency amount of STA medicines was procured as tender failed two times, procurement of the remaining amount was postponed to the next period. Overspending: Euro 36,976 – Actual cost for procurement of methadone, STA essential drugs delayed from Q2 budget. |  | 1150424.2441 | 169300.0424 | 981124.2017 | The expenditure relates to the Medicines and Pharmaceuticals procured locally and directly by The Global Fund. The variance is due to several reasons: Saving: Euro 79,588 – a) Volume of Methadone reduced , based on the quota of methadone for the country, remaining amount agreed with the Drug Regulation Agency will be procured in 2015 within 2015 budget; b) Some drugs not procured due to the avaliable stock at SR ; c) Cheaper unit prices resulted from local procurement Euro 93,811 –Saving in ARVs resulted from actual PQ signed with PPM; Euro 1115 – saving in procurement of essential drugs was made by Aids Center Postponed: Euro 805,451 –Disbursement for ARVs due to the change in the payment method (payment upon delivery) Euro 556 – Procurement of STA drugs postponed to next period (two times tender failed and 3 month’s emergency supply was procured). Commitment: Euro 603 –for procurement of essential drugs in December (Aids Center).
2b. Health products and health equipment | 11716.0147 | 673295.311 | -661579.2963 | The category relates to the Health product/equipment procured locally and with IDA. The variance consists of Negative variance of Euro 670,902 and Positive Variance of Euro 9,323 Postponed: Euro 8364 - Procurement of Tests and lab supplies for objective 4 was included into the service contract with SR CIF (agreed with GF, ref - email of August 5, 2014 ) and will be reimburced in 2015 according to the respective contract with SR. Euro 959 - There was saving in procuring disinfectants due to Available stock at Sr Overspending: Euro 670,902 – Actual cost for Procurement of HPHE delayed from Q2 budget. |  | 1733271.4992 | 673295.311 | 1059976.1882 | The category relates to the Health product/equipment procured locally and with IDA. The variance is due to several reasons: Savings: Euro 868,262 - There was saving in procuring health products and equipment due to the following factors: 1. Local procurement with competitive bidding with preceding market assessment derived cheaper unit costs compared to the budgeted amounts; 2. Available stocks at SRs and Re- calculation of average consumption rates; Postponed: Euro 184,865 - Procurement of health products and equipment including IDA order for syringes and Mobile Laboratories was postponed. The first tender for mobile labs failed, a new one has been anounced and contract will be signed by the end of March, 2015. Euro 26,467- Procurement of Tests and lab supplies for objective 4 was included into the service contract with SR CIF (agreed with GF, ref - email of August 5, 2014 ) and will be reimburced in 2015 according to the respective contract with SR. Overspending: Euro 19,618 - Actual unit cost for some lab supplies occured slightly higher than budgeted (Supplies / consumables for HIVDR; Chlamydia immunofluorescence DFA KIT)

## EFR HIV AIDS Financial Data_3B
SECTION 3B: HIV/AIDS FINANCIAL REPORTING FORM
Country |  | Georgia |  |  | PLEASE REFER TO THE "GUIDANCE FOR COMPLETION OF THE ENHANCED FINANCIAL REPORTING TEMPLATE" DOCUMENT TO ASSIST YOU IN COMPLETING THE TEMPLATE
Grant No. |  | GEO-H-NCDC
PR |  | NCDC |  |  | TO BE COMPLETED ONLY ONCE A YEAR EXCEPT AT MONTH 18 FOR PURPOSES OF PHASE 2 REVIEW
Currency |  | EURO
[6 empty] | dd-mm-yyyy |  |  |  | dd-mm-yyyy
|  |  |  | Current Reporting Period | Start Date: | 2014-04-01 |  | Cumulative Reporting Period | Start Date: | 2014-04-01
[5 empty] | End Date: | 2014-12-31 |  |  | End Date: | 2014-12-31
The end date for the current reporting period and cumulative reporting period must be the same
The "TOTAL" rows in Table A, B and C will have a RED background if the amounts in each table do not agree. If the Totals for each Table agrees, these rows will have a YELLOW background.
A- BREAKDOWN* BY EXPENDITURE CATEGORY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period |  |  |  | All amounts are in: | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
# | Category |  |  | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance | 1. Total PR cash outflow vs. budget | 3370173.8693 | 2752053.64 | 618120.2293 |  | 6365135.8508 | 3127372.9291 | 3237762.9217
1 | Human Resources |  |  | 2117297.923 | 1745016.3472 | 372281.5758 | PR - saving 10293 EUR (some positions remaind vacant during the reporting period); SRs - Remained amount from Commited sums for services provided in December (184,893 EUR) ; Objective 1 related HR cost saved due to postponed implementation - 15114 EUR; remaining saving 161,982EUR is due to delay in procurement of mobile ambulatories, in opening of a new OST and ART Centers and hiring relevant personnel, in addition the cost of case management and reimbursements for medical consultations, monetary incentives for PDI clients was less than budgeted; Also, CIF has a saving in HR due to not using budgeted amount for Q2 for BSS among IDUs (contract was signed with SR end of September) | 2117297.923 | 1745016.3472 | 372281.5758 | PR - saving 10293 EUR (some positions remaind vacant during the reporting period); SRs - Remained amount from Commited sums for services provided in December (184,893 EUR) ; Objective 1 related HR cost saved due to postponed implementation - 15114 EUR; remaining saving 161,982EUR is due to delay in procurement of mobile ambulatories, in opening of a new OST and ART Centers and hiring relevant personnel, in addition the cost of case management and reimbursements for medical consultations, monetary incentives for PDI clients was less than budgeted; Also, CIF has a saving in HR due to not using budgeted amount for Q2 for BSS among IDUs (contract was signed with SR end of September) | 1a. PR's total expenditures | 1512380.6546 | 990032.05 | 522348.6046 |  | 3553454.3749 | 1006122.6851 | 2547331.6898
2 | Technical Assistance |  |  | 147594.3064 | 85804.5084 | 61789.798 | PR - Actual TA cost was less than budgeted by 6,936 EUR; 14773 EUR was postponed for development of HIV prevention database; SRs -24,056 EUR was saved, that includes: 11,116 EUR is committed for December service; Objective 1 postponing resulted in saving of 5,805 EUR; and amount budgeted for harm reduction conference that was canceled: Saving, the management of National AIDS Center couldn't find laboratory expert with required qualification; HAPS Fund hired Study consultant by one month late; Overspanding 896 EUR is reported by CIF that allocated in advance amount from future budget for local consultant for IDU BSS. | 147594.3064 | 85804.5084 | 61789.798 | PR - Actual TA cost was less than budgeted by 6,936 EUR; 14773 EUR was postponed for development of HIV prevention database; SRs -24,056 EUR was saved, that includes: 11,116 EUR is committed for December service; Objective 1 postponing resulted in saving of 5,805 EUR; and amount budgeted for harm reduction conference that was canceled: Saving, the management of National AIDS Center couldn't find laboratory expert with required qualification; HAPS Fund hired Study consultant by one month late; Overspanding 896 EUR is reported by CIF that allocated in advance amount from future budget for local consultant for IDU BSS. | 1b. Disbursements to sub-recipients | 1857793.2147 | 1762021.59 | 95771.6247 |  | 2811681.4759 | 2121250.244 | 690431.2319
3 | Training |  |  | 168123.7059 | 71159.4979 | 96964.208 | PR - 918 is a saving and 21054 is postponed for training of personnel was postponed; SRs - 3069 EUR is committe for December service; 23,309 EUR is postponed for Objective 1 and 11000 for Training of personnel on overdose was postponed by GHRN; remained amount (37613 EUR) is a saving due to changes made in budget lines for staff meetings at the offices of GHRN member organizations, for training of peers, development of IEC materials and organization of round tables for community members; Training of new OST center personnel was postponed by Center for Mental Health and Drug Addiction, drug addiction prevention conference was canceled, participation in international conferences were included into ME category by SR; Tanadgoma spent less amounts per training; AIDS Center had saving in participation cost of international conferences, one of the international visits was canceled; HAPS Fund spent less money for international visit; AIDS victims' memorial day activity was canceled due to lack of institutional money in May; Implementation of Objactive 1 related training was postponed; | 168123.7059 | 71159.4979 | 96964.208 | PR - 918 is a saving and 21054 is postponed for training of personnel was postponed; SRs - 3069 EUR is committe for December service; 23,309 EUR is postponed for Objective 1 and 11000 for Training of personnel on overdose was postponed by GHRN; remained amount (37613 EUR) is a saving due to changes made in budget lines for staff meetings at the offices of GHRN member organizations, for training of peers, development of IEC materials and organization of round tables for community members; Training of new OST center personnel was postponed by Center for Mental Health and Drug Addiction, drug addiction prevention conference was canceled, participation in international conferences were included into ME category by SR; Tanadgoma spent less amounts per training; AIDS Center had saving in participation cost of international conferences, one of the international visits was canceled; HAPS Fund spent less money for international visit; AIDS victims' memorial day activity was canceled due to lack of institutional money in May; Implementation of Objactive 1 related training was postponed;
4 | Health Products and Health Equipment |  |  | 1733271.4992 | 673295.7227 | 1059975.7766 | The expenditure relates to the Health product/equipment procured locally and with IDA. The variance is due to several reasons: Savings: Euro 868,262 - There was saving in procuring health products and equipment due to the following factors: 1. Local procurement with competitive bidding with preceding market assessment derived cheaper unit costs compared to the budgeted amounts; 2. Available stocks at SRs and Re- calculation of average consumption rates; Postponed: Euro 184,865 - Procurement of health products and equipment including IDA order for syringes and Mobile Laboratories was postponed. The first tender for mobile labs failed, a new one has been announced and contract will be signed by the end of March, 2015. Euro 28,860 - Procurement of Tests and lab supplies for objective 4 was included into the service contract with SR CIF (agreed with GF, ref - email of August 5, 2014 ) and will be reimbursed in 2015 according to the respective contract with SR. Overspending: Euro 19,618 - Actual unit cost for some lab supplies occurred slightly higher than budgeted (Supplies / consumables for HIVDR; Chlamydia immunofluorescence DFA KIT) SR level - CIF allocated amount from HR category for covering cost of test-kits (HPHE category) | 1733271.4992 | 673295.7227 | 1059975.7766 | The expenditure relates to the Health product/equipment procured locally and with IDA. The variance is due to several reasons: Savings: Euro 868,262 - There was saving in procuring health products and equipment due to the following factors: 1. Local procurement with competitive bidding with preceding market assessment derived cheaper unit costs compared to the budgeted amounts; 2. Available stocks at SRs and Re- calculation of average consumption rates; Postponed: Euro 184,865 - Procurement of health products and equipment including IDA order for syringes and Mobile Laboratories was postponed. The first tender for mobile labs failed, a new one has been announced and contract will be signed by the end of March, 2015. Euro 28,860 - Procurement of Tests and lab supplies for objective 4 was included into the service contract with SR CIF (agreed with GF, ref - email of August 5, 2014 ) and will be reimbursed in 2015 according to the respective contract with SR. Overspending: Euro 19,618 - Actual unit cost for some lab supplies occurred slightly higher than budgeted (Supplies / consumables for HIVDR; Chlamydia immunofluorescence DFA KIT) SR level - CIF allocated amount from HR category for covering cost of test-kits (HPHE category) |  | Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
5 | Medicines and Pharmaceutical Products |  |  | 1150424.2441 | 169300.3437 | 981123.9004 | The expenditure relates to the Medicines and Pharmaceuticals procured locally and directly by The Global Fund. The variance is due to several reasons: Saving: Euro 79,588 – a) Volume of Methadone reduced , based on the quota of methadone for the country, remaining amount agreed with the Drug Regulation Agency will be procured in 2015 within 2015 budget; b) Some drugs not procured due to the avaliable stock at SR ; c) Cheaper unit prices resulted from local procurement Euro 93,811 –Saving in ARVs resulted from actual PQ signed with PPM; Euro 1115 – saving in procurement of essential drugs was made by Aids Center Postponed: Euro 805,451 –Disbursement for ARVs due to the change in the payment method (payment upon delivery) Euro 556 – Procurement of STA drugs postponed to next period (two times tender failed and 3 month’s emergency supply was procured). Commitment: Euro 603 –for procurement of essential drugs in December (Aids Center). | 1150424.2441 | 169300.3437 | 981123.9004 | The expenditure relates to the Medicines and Pharmaceuticals procured locally and directly by The Global Fund. The variance is due to several reasons: Saving: Euro 79,588 – a) Volume of Methadone reduced , based on the quota of methadone for the country, remaining amount agreed with the Drug Regulation Agency will be procured in 2015 within 2015 budget; b) Some drugs not procured due to the avaliable stock at SR ; c) Cheaper unit prices resulted from local procurement Euro 93,811 –Saving in ARVs resulted from actual PQ signed with PPM; Euro 1115 – saving in procurement of essential drugs was made by Aids Center Postponed: Euro 805,451 –Disbursement for ARVs due to the change in the payment method (payment upon delivery) Euro 556 – Procurement of STA drugs postponed to next period (two times tender failed and 3 month’s emergency supply was procured). Commitment: Euro 603 –for procurement of essential drugs in December (Aids Center). | 2. Total pharmaceutical & health product expenditures vs. budget | 1051878.3797 | 842595.3534 | 209283.0263 |  | 2883695.7433 | 842595.3534 | 2041100.3899
6 | Procurement and Supply Management Costs |  |  | 232128.2006 | 3752.1597 | 228376.0409 | PR - 85220 EUR is postponed ARV PSM actual cost; 145,343 EUR is a saving in ARV procurement based on signed PQ; SRs - 887 EUR is committed by GHRN for December; 1147 EUR is overspending by GHRN (money for future period was allocated); 1957 Eur is a change of category by SR (MHDAC) from OVE to PSM; | 232128.2006 | 3752.1597 | 228376.0409 | PR - 85220 EUR is postponed ARV PSM actual cost; 145,343 EUR is a saving in ARV procurement based on signed PQ; SRs - 887 EUR is committed by GHRN for December; 1147 EUR is overspending by GHRN (money for future period was allocated); 1957 Eur is a change of category by SR (MHDAC) from OVE to PSM; | 2a. Medicines and pharmaceutical products | 1040162.365 | 169300.0424 | 870862.3226 |  | 1150424.2441 | 169300.0424 | 981124.2017
7 | Infrastructure and Other Equipment |  |  | 158485.1348 | 31382.3429 | 127102.792 | PR - 66196 EUR is a saving (procurement of cars was canceled, database upgrade for AIDS Center was moved to SRs contract, renovation costs for Telavi AIDS Center and Project management cost) Postponed 38,864 EUR - new OST Center related IE cost, office equipment for SRs, ERP system SRs - 1474 is committed for December, Saving 14503 EUR (car maintenance actual costs were less than budgeted) 6065 EUR is postponed from Objective 1 budget | 158485.1348 | 31382.3429 | 127102.792 | PR - 66196 EUR is a saving (procurement of cars was canceled, database upgrade for AIDS Center was moved to SRs contract, renovation costs for Telavi AIDS Center and Project management cost) Postponed 38,864 EUR - new OST Center related IE cost, office equipment for SRs, ERP system SRs - 1474 is committed for December, Saving 14503 EUR (car maintenance actual costs were less than budgeted) 6065 EUR is postponed from Objective 1 budget | 2b. Health products and health equipment | 11716.0147 | 673295.311 | -661579.2963 |  | 1733271.4992 | 673295.311 | 1059976.1882
8 | Communication Materials |  |  | 44742.6893 | 7596.6813 | 37146.0079 | PR - 33,608 EUR is saving in printing of IEC materials procured through tender, delay in implementation of media campaign (801 Eur is postponed) SRs - comitted 441 EUR, saving - 1,999 EUR and 303 EUR is postponed from Objective 1. | 44742.6893 | 7596.6813 | 37146.0079 | PR - 33,608 EUR is saving in printing of IEC materials procured through tender, delay in implementation of media campaign (801 Eur is postponed) SRs - comitted 441 EUR, saving - 1,999 EUR and 303 EUR is postponed from Objective 1.
9 | Monitoring & Evaluation |  |  | 135362.43 | 63305.1506 | 72057.2794 | PR - 16290 Eur is saving from fuel procurement and less than budgeted amount was spent on M&E visits; 273 Eur is committed for December fuel; SRs - committed is 12,509 EUR, 7817 EUR is postponed, overspending is 1476 EUR MHDAC has moved TA categoty cost to M&E; saving is 36808 EUR (AIDS Center's data entry personnel wasn't hired, telavi Center personnel and transportation cost for Abkhazia) | 135362.43 | 63305.1506 | 72057.2794 | PR - 16290 Eur is saving from fuel procurement and less than budgeted amount was spent on M&E visits; 273 Eur is committed for December fuel; SRs - committed is 12,509 EUR, 7817 EUR is postponed, overspending is 1476 EUR MHDAC has moved TA categoty cost to M&E; saving is 36808 EUR (AIDS Center's data entry personnel wasn't hired, telavi Center personnel and transportation cost for Abkhazia)
10 | Living Support to Clients/Target Populations |  |  | 91324.4988 | 49845.2367 | 41479.2621 | PR- N/A SR- 5,553 is comitted for PDI incentives and Milk Formula for PLHIV positive mothers newborns; Saving 35927 is a saving in PDI incentives as actual demand from IDUs and MSM were less than anticipated and budgeted | 91324.4988 | 49845.2367 | 41479.2621 | PR- N/A SR- 5,553 is comitted for PDI incentives and Milk Formula for PLHIV positive mothers newborns; Saving 35927 is a saving in PDI incentives as actual demand from IDUs and MSM were less than anticipated and budgeted
11 | Planning and Administration |  |  | 27794.1972 | 13918.8283 | 13875.3688 | PR - EUR 6,988 was saved due to less amount allocated for Tenders anouncement; SRs- EUR 1,474 is comitted for December, EUR 173 is Objective 1 related and postponed; saving is EUR 5,240 as SRs spent less money for procurement of office supplies | 27794.1972 | 13918.8283 | 13875.3688 | PR - EUR 6,988 was saved due to less amount allocated for Tenders anouncement; SRs- EUR 1,474 is comitted for December, EUR 173 is Objective 1 related and postponed; saving is EUR 5,240 as SRs spent less money for procurement of office supplies
12 | Overheads |  |  | 358587.0214 | 203836.9823 | 154750.0391 | PR - Saving was in procurement of fuel through consolidated tender 36,023 EUR 15446 EUR project management cost related saving; committed 5417 EUR is committed for Fuel and GSM cost; postponed 1083 EUR ; SRs - committed 22,071 EUR for December utilities, objective 1 - 2599 EUR; saving 71947 -The saving was made in preparation of plastic clients' cards of PWIDs, in procurement of medical and art supplies, not spending money budgeted for OVE costs related to operation of mobile ambulatories and of new OST Centers; less amounts were spent for utilities during spring-summer period; National AIDS Center saved some amount as opening of Telavi ART Center was postponed and money for transportation of medical supplies to Abkhazia was saved; | 358587.0214 | 203836.9823 | 154750.0391 | PR - Saving was in procurement of fuel through consolidated tender 36,023 EUR 15446 EUR project management cost related saving; committed 5417 EUR is committed for Fuel and GSM cost; postponed 1083 EUR ; SRs - committed 22,071 EUR for December utilities, objective 1 - 2599 EUR; saving 71947 -The saving was made in preparation of plastic clients' cards of PWIDs, in procurement of medical and art supplies, not spending money budgeted for OVE costs related to operation of mobile ambulatories and of new OST Centers; less amounts were spent for utilities during spring-summer period; National AIDS Center saved some amount as opening of Telavi ART Center was postponed and money for transportation of medical supplies to Abkhazia was saved;
13 | Other |  |  | 0 | 0 |  |  | 0 | 0
|  |  | TOTAL | 6365135.8508 | 3118213.8018 | 3246922.049 |  | 6365135.8508 | 3118213.8018 | 3246922.049
B- BREAKDOWN* BY PROGRAM ACTIVITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Macro-category | Objectives | Service Delivery Area | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
1 | Supportive Environment | To establish supportive environment for HIV/AIDS prevention, treatment, care and support | Supportive environment: Stigma reduction in all settings | 54612.1047 | 0 | 54612.1047 | Postponed implementation , delay due to market search and preparation of tender documentation, tenders are conducted and implementing organizations are revealed (strengthening of LGBT community – NGO Tanadgoma; Strengthening of HIV community and Advocacy- NGO real vision, real people; training of HCWs- HAPS Fund), others will be completed by end of March. | 54612.1047 | 0 | 54612.1047 | Postponed implementation , delay due to market search and preparation of tender documentation, tenders are conducted and implementing organizations are revealed (strengthening of LGBT community – NGO Tanadgoma; Strengthening of HIV community and Advocacy- NGO real vision, real people; training of HCWs- HAPS Fund), others will be completed by end of March.
2 | Prevention | To increase coverage and quality of preventive interventions targeted at MARPs | Prevention: Behavioral Change Communication - community outreach | 3012455.0025 | 1754403.9261 | 1258051.0765 | PR – 643,776 EURO is a saving in objective 2 related procurement including IDA procurement of condoms, due to lower price achieved through tender procurement and available stocks with SRs. Committed – 3,289 EURO – for fuel of December; 220,427 EURO procurement is postponed – Mobile laboratories, Office Renovation of new OST Center, IDA condom PQ reimbursement; 1598 EURO is a minor overspending in procurement of some tests and medical gloves SRs – Saving 225,005 EURO, Committed amount 160,773 EURO for December services Postponed 11,000 EURO – amount for training on overdose of medical personnel by GHRN Overspending 4580 EURO (1147 EURO is advance from future budget – GHRN for PSM cost) The main contribution to the variance is the category due to delay in procurement of mobile ambulatories and hiring relevant personnel for GHRN, however, in order to address the need to increase coverage of IDUs with outreach services, PR allowed SR to hire staff for Mobile Ambulatory in advance who started outreach work with ordinary cars, this way negative impact to the program was mostly mitigated; There was a delay in opening of a new OST Center as well and all related costs were saved; Despite of this delay, there was no negative impact on the program implementation as Government abolished setting limits per OST center for number of patients served and GF OST Centers also could serve more patients, the target OST patients' indicator was overachieved; the cost is related to PDI interventions were paid based on the actual number of clients (PWIDs, FSWs and MSM) served; less number of VCT consultants were working in prisons; less amount was spent per training, less amount was spent for technical services of cars and office equipment, design of IEC materials, per M&E visits, saving was in procurement of office supplies (stationary), in expenses related to rent and utilities; The SRs have considerably improved the coverage data, but there is still room for rather improvements that will be facilitated with procurement of mobile ambulatory cars, opening of new OST Center and expanding PDI activities among MSM that should good results. | 3012455.0025 | 1754403.9261 | 1258051.0765 | PR – 643,776 EURO is a saving in objective 2 related procurement including IDA procurement of condoms, due to lower price achieved through tender procurement and available stocks with SRs. Committed – 3,289 EURO – for fuel of December; 220,427 EURO procurement is postponed – Mobile laboratories, Office Renovation of new OST Center, IDA condom PQ reimbursement; 1598 EURO is a minor overspending in procurement of some tests and medical gloves SRs – Saving 225,005 EURO, Committed amount 160,773 EURO for December services Postponed 11,000 EURO – amount for training on overdose of medical personnel by GHRN Overspending 4580 EURO (1147 EURO is advance from future budget – GHRN for PSM cost) The main contribution to the variance is the category due to delay in procurement of mobile ambulatories and hiring relevant personnel for GHRN, however, in order to address the need to increase coverage of IDUs with outreach services, PR allowed SR to hire staff for Mobile Ambulatory in advance who started outreach work with ordinary cars, this way negative impact to the program was mostly mitigated; There was a delay in opening of a new OST Center as well and all related costs were saved; Despite of this delay, there was no negative impact on the program implementation as Government abolished setting limits per OST center for number of patients served and GF OST Centers also could serve more patients, the target OST patients' indicator was overachieved; the cost is related to PDI interventions were paid based on the actual number of clients (PWIDs, FSWs and MSM) served; less number of VCT consultants were working in prisons; less amount was spent per training, less amount was spent for technical services of cars and office equipment, design of IEC materials, per M&E visits, saving was in procurement of office supplies (stationary), in expenses related to rent and utilities; The SRs have considerably improved the coverage data, but there is still room for rather improvements that will be facilitated with procurement of mobile ambulatory cars, opening of new OST Center and expanding PDI activities among MSM that should good results.
3 | Treatment | To sustain treatment, care and support for PLHIV including Abkhazia frozen conflict area |  | 2801578.1772 | 1093241.6133 | 1708336.5639 | PR – saving 660,232 EURO procurement of ARVs (actual contract with PPM lower prices of drugs, PSM and PPM fee); lower tender prices in procurement of diagnostic kits and lab supplies, stocks available; canceled procurement of diagnostic kits for tropism, Postponed payment for ARVs (reimbursement will be made upon delivery in 2015) and office furniture - 900,235 ARV; Committed: 1690 EURO fuel for December Overspending: 18309 EURO in procurement of lab supplies SR level – AIDS Center -Saving 95,889 EURO; committed 50,730 EURO for December service cost; postponed 2274 EURO for data entry personnel Saving was due to delay in hiring of planned additional personnel for treatment centers (they couldn't find relevant professionals with required qualification), hiring of laboratory expert with relevant background and experience and postponing and later canceling of opening of new ART regional center in Telavi as it wasn't possible to find suitable health care institution that would host such specialized treatment facility. Less than budgeted amounts were spent for technical service of cars and medical and laboratory equipment; SR hired late data entry personnel, it paid less for international laboratory quality control service, saving was also in procurement of office supplies, in utilities and administrative costs and in transportation of supplies to Abkhazia. Despite canceling of opening of new ART Center in Telavi (Kakheti), the SR still had good achievements related to ART indicators as PLHIV living in Kakheti region were receiving the service at National AIDS Center in Tbilisi from more skillful professionals than they would receive in regions. Although, many of patients would prefer receiving treatment in Tbilisi due to confidentiality concerns. HAPS Fund – committed 8,738 EURO for December service; Saving is 6,856 EURO in HR and OVE (rent and utilities) | 2801578.1772 | 1093241.6133 | 1708336.5639 | PR – saving 660,232 EURO procurement of ARVs (actual contract with PPM lower prices of drugs, PSM and PPM fee); lower tender prices in procurement of diagnostic kits and lab supplies, stocks available; canceled procurement of diagnostic kits for tropism, Postponed payment for ARVs (reimbursement will be made upon delivery in 2015) and office furniture - 900,235 ARV; Committed: 1690 EURO fuel for December Overspending: 18309 EURO in procurement of lab supplies SR level – AIDS Center -Saving 95,889 EURO; committed 50,730 EURO for December service cost; postponed 2274 EURO for data entry personnel Saving was due to delay in hiring of planned additional personnel for treatment centers (they couldn't find relevant professionals with required qualification), hiring of laboratory expert with relevant background and experience and postponing and later canceling of opening of new ART regional center in Telavi as it wasn't possible to find suitable health care institution that would host such specialized treatment facility. Less than budgeted amounts were spent for technical service of cars and medical and laboratory equipment; SR hired late data entry personnel, it paid less for international laboratory quality control service, saving was also in procurement of office supplies, in utilities and administrative costs and in transportation of supplies to Abkhazia. Despite canceling of opening of new ART Center in Telavi (Kakheti), the SR still had good achievements related to ART indicators as PLHIV living in Kakheti region were receiving the service at National AIDS Center in Tbilisi from more skillful professionals than they would receive in regions. Although, many of patients would prefer receiving treatment in Tbilisi due to confidentiality concerns. HAPS Fund – committed 8,738 EURO for December service; Saving is 6,856 EURO in HR and OVE (rent and utilities)
4 | Health System Strengthening (HSS) | To generate evidences and document HIV program effectiveness | HSS: Information system & Operational research | 266519.7963 | 135808.3878 | 130711.4085 | PR – saving in procurement of fuel 13,024 EURO for AIDS center and CIF Committed 495 EURO for fuel for December; postponed – 28,860 (CIF test systems cost of HPHE category) SRs – Saving 53,533 EURO (CIF Saving due to not using budgeted amount for Q2 for BSS among IDUs (contract was signed with SR end of September), 4300 EURO is postponed - the request for reimbursement of laboratory testing conducted in November-December of 2014 was presented late (in January,2015); Committed is 20,731 EURO for CIF (December service cost) Due to late start of the BSS among IDUs the PR and SR couldn’t present the relevant impact indicator data in February and will be submitting this information in May when the official report will be available. Meantime, CIF will provide preliminary HIV prevalence data among IDUs that will be used during the development of CN. Overspending 3290 EURO – reallocation from HR to PHPE for test-systems and future budget allocation for local consultant by CIF AIDS Center : saving is 9853 in implementation of drug resistance survey, committed is 3,158 EURO for December service reimbursement; HAPS Fund- saving of 46 EURO | 266519.7963 | 135808.3878 | 130711.4085 | PR – saving in procurement of fuel 13,024 EURO for AIDS center and CIF Committed 495 EURO for fuel for December; postponed – 28,860 (CIF test systems cost of HPHE category) SRs – Saving 53,533 EURO (CIF Saving due to not using budgeted amount for Q2 for BSS among IDUs (contract was signed with SR end of September), 4300 EURO is postponed - the request for reimbursement of laboratory testing conducted in November-December of 2014 was presented late (in January,2015); Committed is 20,731 EURO for CIF (December service cost) Due to late start of the BSS among IDUs the PR and SR couldn’t present the relevant impact indicator data in February and will be submitting this information in May when the official report will be available. Meantime, CIF will provide preliminary HIV prevalence data among IDUs that will be used during the development of CN. Overspending 3290 EURO – reallocation from HR to PHPE for test-systems and future budget allocation for local consultant by CIF AIDS Center : saving is 9853 in implementation of drug resistance survey, committed is 3,158 EURO for December service reimbursement; HAPS Fund- saving of 46 EURO
5 | Supportive Environment | PR Management and Administration | Supportive environment: Program management and administration | 229970.7701 | 134759.8746 | 95210.8955 | PR: Saving – 62,960 EURO Committed 216 EURO for fuel cost for December Postponed 32,035 EURO (ERP, fire alarm system installation, Training for PR staff and media campaign implementation) | 229970.7701 | 134759.8746 | 95210.8955 | PR: Saving – 62,960 EURO Committed 216 EURO for fuel cost for December Postponed 32,035 EURO (ERP, fire alarm system installation, Training for PR staff and media campaign implementation)
TOTAL |  |  |  | 6365135.8508 | 3118213.8018 | 3246922.049 |  | 6365135.8508 | 3118213.8018 | 3246922.049
To add additional rows, right click the row number (Row 39 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
C- BREAKDOWN* BY IMPLEMENTING ENTITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | PR/SR | Name | Type of Implementing Entity | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
1 | SR | TBD | Please Select… | 54612.1047 | 0 | 54612.1047 | Postponed implementation , delay due to market search and preparation of tender documentation, tenders are conducted and implementing organizations are revealed (strengthening of LGBT community – NGO Tanadgoma; Strengthening of HIV community and advocacy - NGO real vision, real people; training of HCWs- HAPS Fund), | 54612.1047 | 0 | 54612.1047 | Postponed implementation , delay due to market search and preparation of tender documentation, tenders are conducted and implementing organizations are revealed (strengthening of LGBT community – NGO Tanadgoma; Strengthening of HIV community and advocacy - NGO real vision, real people; training of HCWs- HAPS Fund),
2 | SR | Georgian Harm Reducation Network | NGO/CBO/Academic | 1029605.7306 | 787519.4435 | 242086.287 | Saving – 137,496 EURO Committed 94,738 EURO for December service; The main contribution to the variance is the delay in procurement of mobile ambulatories and hiring relevant personnel, that caused savings in HR, ME and OVE categories, in order to address the need to increase coverage of IDUs with outreach services, PR allowed SR to hire staff for Mobile Ambulatory in advance who started outreach work with ordinary cars, this way negative impact to the program was mitigated; Saving was also in cost of case management, reimbursements for medical consultations, less amount was disbursed as PDI incentives; savings were in technical services of cars and office equipment, stationary procurement, in preparation of plastic service cards, in expenses related to utilities; in procurement of art supplies; Saving is also amount budgeted for harm reeducation conference wasn't spent due to technical problems in planning; Training of personnel on overdose was postponed; Savings were made in budget lines for staff meetings at the offices of GHRN member organizations, for training of peers, participation in international conferences, development of IEC materials and organization of round tables for community members as the less amount was spent per event than was budgeted. Postponed 11000 EURO for training on overdose for HCWs Overspending 1147 EURO -Overspending was in category PSM as spending depends on the volume of supplies to be delivered, SR had to use advance from future budget to cover the actual costs of transportation of goods | 1029605.7306 | 787519.4435 | 242086.287 | Saving – 137,496 EURO Committed 94,738 EURO for December service; The main contribution to the variance is the delay in procurement of mobile ambulatories and hiring relevant personnel, that caused savings in HR, ME and OVE categories, in order to address the need to increase coverage of IDUs with outreach services, PR allowed SR to hire staff for Mobile Ambulatory in advance who started outreach work with ordinary cars, this way negative impact to the program was mitigated; Saving was also in cost of case management, reimbursements for medical consultations, less amount was disbursed as PDI incentives; savings were in technical services of cars and office equipment, stationary procurement, in preparation of plastic service cards, in expenses related to utilities; in procurement of art supplies; Saving is also amount budgeted for harm reeducation conference wasn't spent due to technical problems in planning; Training of personnel on overdose was postponed; Savings were made in budget lines for staff meetings at the offices of GHRN member organizations, for training of peers, participation in international conferences, development of IEC materials and organization of round tables for community members as the less amount was spent per event than was budgeted. Postponed 11000 EURO for training on overdose for HCWs Overspending 1147 EURO -Overspending was in category PSM as spending depends on the volume of supplies to be delivered, SR had to use advance from future budget to cover the actual costs of transportation of goods
3 | SR | Center of Mental Health and Prevention of Drug Addiction | Other Government | 473750.7415 | 383799.7042 | 89951.0374 | Saving – 46648 EURO Saving is mainly results of delays in opening of new OST center, especially in HR, T, ME, PA and OVE categories; personnel wasn't hired, wasn't trained and related administrative and overhead costs were saved; Less than budgeted amounts were spent on repair of observation cameras, technical services of cars and office equipment, on round tables, in procurement of art supplies, in monetary incentives for PWIDs, for office supplies, in utilities' and security costs. Drug Addiction Prevention Day Conference was canceled due to technical reasons, participation in international conferences were included into ME category, while it was initially budgeted in the OVE in approved GF budget; Despite delay in opening of new OST center there was no negative impact on the program implementation as Government abolished setting limits per OST center for number of patients served and GF OST Centers also could serve more patients, the target OST patients' indicator was overachieved Committed for December service 46,736 EURO Changes in category by SR in tender proposal – OVE 1957 to PSM and 1476 EURO from T to ME category | 473750.7415 | 383799.7042 | 89951.0374 | Saving – 46648 EURO Saving is mainly results of delays in opening of new OST center, especially in HR, T, ME, PA and OVE categories; personnel wasn't hired, wasn't trained and related administrative and overhead costs were saved; Less than budgeted amounts were spent on repair of observation cameras, technical services of cars and office equipment, on round tables, in procurement of art supplies, in monetary incentives for PWIDs, for office supplies, in utilities' and security costs. Drug Addiction Prevention Day Conference was canceled due to technical reasons, participation in international conferences were included into ME category, while it was initially budgeted in the OVE in approved GF budget; Despite delay in opening of new OST center there was no negative impact on the program implementation as Government abolished setting limits per OST center for number of patients served and GF OST Centers also could serve more patients, the target OST patients' indicator was overachieved Committed for December service 46,736 EURO Changes in category by SR in tender proposal – OVE 1957 to PSM and 1476 EURO from T to ME category
4 | SR | Tanadgoma | NGO/CBO/Academic | 395562.7076 | 335442.2246 | 60120.483 | Saving 40,862 EURO In cost of rent and utilities as SR was covering this cost from other programs also; the cost is related to PDI interventions were paid based on the actual number of clients served; less number of VCT consultants were working in prisons; less amount was spent per training, less amount was spent for technical services of cars and office equipment, design of IEC materials, per M&E visits, actual disbursed amount for popular leader program activists and PDI cash incentives was less than budgeted; saving was in procurement of office supplies (stationary), in expenses related to rent and utilities; also, preparation of key chain plastic cards for MSM was canceled. The SR has mostly implemented all planned activities and has improved its coverage data for both key population groups (FSWs and MSM). During implementation period SR has addressed the PR regarding changes in the program implementation asking to test PDI interventions among MSM as it wasn’t much successful among FSWs. PR has agreed on this change with support of FPM and the activity showed better results for MSM population and allowed the SR to increase their coverage with prevention package. PDI activities are expended to regions also (Batumi, Kutaisi). Committed: 19,259 EURO for December service cost; | 395562.7076 | 335442.2246 | 60120.483 | Saving 40,862 EURO In cost of rent and utilities as SR was covering this cost from other programs also; the cost is related to PDI interventions were paid based on the actual number of clients served; less number of VCT consultants were working in prisons; less amount was spent per training, less amount was spent for technical services of cars and office equipment, design of IEC materials, per M&E visits, actual disbursed amount for popular leader program activists and PDI cash incentives was less than budgeted; saving was in procurement of office supplies (stationary), in expenses related to rent and utilities; also, preparation of key chain plastic cards for MSM was canceled. The SR has mostly implemented all planned activities and has improved its coverage data for both key population groups (FSWs and MSM). During implementation period SR has addressed the PR regarding changes in the program implementation asking to test PDI interventions among MSM as it wasn’t much successful among FSWs. PR has agreed on this change with support of FPM and the activity showed better results for MSM population and allowed the SR to increase their coverage with prevention package. PDI activities are expended to regions also (Batumi, Kutaisi). Committed: 19,259 EURO for December service cost;
5 | SR | Infectious Diseases, AIDS and Clinical Immunology Research Center | Other Government | 573126.0424 | 411220.8093 | 161905.2331 | Saving: 105,742 EURO Main reason for saving was a delay in hiring of planned additional personnel for treatment centers (they couldn't find relevant professionals with required qualification), hiring of laboratory expert with relevant background and experience and postponing and later canceling of opening of new ART regional center in Telavi as it wasn't possible to find suitable health care institution that would host such specialized treatment facility. Less than budgeted amounts were spent for technical service of cars and medical and laboratory equipment; for international training/conference (one visit was canceled) SR paid less for international laboratory quality control service, saving was also in procurement of office supplies, in utilities and administrative costs and in transportation of supplies to Abkhazia. Despite canceling of opening of new ART Center in Telavi (Kakheti), the SR still had good achievements related to ART indicators as PLHIV living in Kakheti region were receiving the service at National AIDS Center in Tbilisi from more skillful professionals than they would receive in regions. Although, many of patients would prefer receiving treatment in Tbilisi due to confidentiality concerns. Committed: 53,889 EURO December service cost Postponed: 2275 EURO salaries of data entry personnel | 573126.0424 | 411220.8093 | 161905.2331 | Saving: 105,742 EURO Main reason for saving was a delay in hiring of planned additional personnel for treatment centers (they couldn't find relevant professionals with required qualification), hiring of laboratory expert with relevant background and experience and postponing and later canceling of opening of new ART regional center in Telavi as it wasn't possible to find suitable health care institution that would host such specialized treatment facility. Less than budgeted amounts were spent for technical service of cars and medical and laboratory equipment; for international training/conference (one visit was canceled) SR paid less for international laboratory quality control service, saving was also in procurement of office supplies, in utilities and administrative costs and in transportation of supplies to Abkhazia. Despite canceling of opening of new ART Center in Telavi (Kakheti), the SR still had good achievements related to ART indicators as PLHIV living in Kakheti region were receiving the service at National AIDS Center in Tbilisi from more skillful professionals than they would receive in regions. Although, many of patients would prefer receiving treatment in Tbilisi due to confidentiality concerns. Committed: 53,889 EURO December service cost Postponed: 2275 EURO salaries of data entry personnel
6 | SR | HIV/AIDS Patients Support Foundation | NGO/CBO/Academic | 107910.3405 | 92269.5297 | 15640.8108 | Saving: 6903 EURO – Ove and HR categories mainly Saving, less amount was spent on HR due to late signing of the contracts with staff, expert for survey was hired by one month late; SR spend less money for international visit; AIDS victims' memorial day activity was canceled due to lack of institutional money before getting cash advance in May; Saving was in technical service of office equipment and procurement office supplies, in cost of utilities and office rent. There was no any noticeable impact due to not fully utilizing the budgeted amount on the program implementation Committed: 8738 EURO for December service | 107910.3405 | 92269.5297 | 15640.8108 | Saving: 6903 EURO – Ove and HR categories mainly Saving, less amount was spent on HR due to late signing of the contracts with staff, expert for survey was hired by one month late; SR spend less money for international visit; AIDS victims' memorial day activity was canceled due to lack of institutional money before getting cash advance in May; Saving was in technical service of office equipment and procurement office supplies, in cost of utilities and office rent. There was no any noticeable impact due to not fully utilizing the budgeted amount on the program implementation Committed: 8738 EURO for December service
7 | SR | Curatio International Foundation | Private Sector | 177113.8086 | 101839.4054 | 75274.4033 | Saving: 53,533 EURO Committed: 20731 EURO Postponed: 4300 EURO the request for reimbursement of laboratory testing conducted in November-December of 2014 was presented late (in January,2015); Overspending 3290 EURO – local consultant cost Saving due to not using budgeted amount for Q2 for BSS among IDUs (contract was signed with SR end of September), less amount was paid to interviewers (unit cost was reduced); Due to late start of the BSS among IDUs the PR and SR couldn’t present the relevant impact indicator data in February and will be submitting this information in May,2015 when the official report will be available. Meantime, CIF will provide preliminary HIV prevalence data among IDUs that will be used during the development of CN. | 177113.8086 | 101839.4054 | 75274.4033 | Saving: 53,533 EURO Committed: 20731 EURO Postponed: 4300 EURO the request for reimbursement of laboratory testing conducted in November-December of 2014 was presented late (in January,2015); Overspending 3290 EURO – local consultant cost Saving due to not using budgeted amount for Q2 for BSS among IDUs (contract was signed with SR end of September), less amount was paid to interviewers (unit cost was reduced); Due to late start of the BSS among IDUs the PR and SR couldn’t present the relevant impact indicator data in February and will be submitting this information in May,2015 when the official report will be available. Meantime, CIF will provide preliminary HIV prevalence data among IDUs that will be used during the development of CN.
8 | PR | National Center for Disease Control and Public Health | Please Select… | 3553454.3749 | 1006122.6851 | 2547331.6898 | Main cause for the variance is delay in payment to PPM for ARV medicines, some positions remained vacant during the reporting period, Objective 1 implementation was postponed, savings were made in local procurement of products based on the better prices achieved during tenders | 3553454.3749 | 1006122.6851 | 2547331.6898 | Main cause for the variance is delay in payment to PPM for ARV medicines, some positions remained vacant during the reporting period, Objective 1 implementation was postponed, savings were made in local procurement of products based on the better prices achieved during tenders
|  |  | TOTAL | 6365135.8508 | 3118213.8018 | 3246922.049 |  | 6365135.8508 | 3118213.8018 | 3246922.049
To add additional rows, right click the row number (Row 51 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
* The sum of all three breakdowns should be equal (A- Budget Line-item, B- Program Activity, C- Implementing Entity).
** For the purposes of this report, the SDA Program management and administration should be included in the Supportive Environment Macro Category.
D- ADDITIONAL INFORMATION
Please disclose any relevant information concerning the information in the above tables. Refer to the Guidelines for Completing the Template if required.
The actual expenses of SRs include the reimbursement for June – November, 2014 expenses (except for GHRN, which includes April-November, 2014). This results in variances compared to approved SR budgets of Q2/Q3. During Dec-2014 some SRs were using advance payments received from PR for the implementation of the planned activities, others were allocating their own money to cover programmatic activities. These SR moneys are not material and are not included in the current EFR
E- DISBURSEMENTS BREAKDOWN BY IMPLEMENTING ENTITY |  |  |  | Cumulative Reporting Period
# | Name | Type of Implementing Entity | Cumulative Disbursements | Comments
1 | Georgian Harm Reducation Network | NGO/CBO/Academic | 787519.4562 | PR payments to the SR for April-November services.
2 | Center of Mental Health and Prevention of Drug Addiction | Other Government | 383799.7042 | PR payments to the SR for April-November services.
3 | Tanadgoma | NGO/CBO/Academic | 341108.3836 | PR payments to the SR for April-November services., plus advance payment for December
4 | Infectious Diseases, AIDS and Clinical Immunology Research Center | Other Government | 411220.8093 | PR payments to the SR for April-November services.
5 | HIV/AIDS Patients Support Foundation | NGO/CBO/Academic | 95762.4853 | PR payments to the SR for April-November services., plus advance payment for December
6 | Curatio International Foundation | Private Sector | 101839.4054 | PR payments to the SR for April-November services.
|  | TOTAL | 2121250.244
Note on A34: Insert Number
Note on A46: Insert Number
Note on A72: Insert Number
Note on B29: This category should only be used as a last resort if there is a type of cost that absolutely cannot be allocated to another cost category
Note on C34: Please remember to include the full name of the objective. If an objective has more than 1 SDA, repeat the objective name on each row for the relevant SDA
Note on C72: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D46: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D79: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on E40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on E55: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E71: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on E72: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on F30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on F40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on F55: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on G8: Start date for current period cannot be earlier than cumulative period
Note on G30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on G40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on G55: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on H16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on I15: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I20: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I21: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I30: Please ensure that: -the figure here agrees with the figure in the corresponding cells in Tables B and C (in this tab). If they do not the background color will be RED; and -the figure also agrees with the cumulative budget figure in the corresponding cell (H11) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I33: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on I45: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I55: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on J20: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J21: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on J40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on J55: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on K8: Start date for current period cannot be earlier than cumulative period
Note on K30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on K40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on K55: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on L16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.

## PR_Procurement Info_4
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | GEO-H-NCDC
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: | 2
Section 4: Procurement and Supply Management
Comments
1a. Have you updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? If health products procurement information has not been entered into the PQR, please explain why. ! For further guidance on PQR data entry, please refer to the guidelines. |  |  | Yes | Prices and other required details for following items procured in the covered period was uploaded to the PQR system: 1.HIV RDT & EIA- Advanced quality one-step Anti-HIV (1&2) Tests; - GF-H/ET/G/53 2.HIV virological testing equipment: a) Roche Molecular Systems, Inc. USA - COBAS Taq Man HIV-1 Test; - contract # GF-H/ET/G/94 b) Abbot Molecular inc. USA - contract # GF-H/Et/G-92 I. m Sample Preparation System RNA ( 4x24 Preps) [04J70-24] II. Abbott RealTime HIV-1 qualititative Amplification Reagent Kit 96 tests [00884999009578]; c) Nuclisens EasyMag Magnec Silica 384 Extractions ( 280133); NucliSens Easy HIV-1 v2.0 (Automated) 48s/4L ( 280130)- contract # GF-H/ET/G /50 d) ViroSeqHIV-1 Genotyping System V2.0 CE; contract# GF-H/ET/G/42 3. HIV CD4 testing consumables /test kits- a)Partec CD4 easy count kits; contract # GF-H/Et/G/36 b) BD FACS, Multi Test trucount tests; # GF-H/ET/G/40 4.Male Latex Condoms - R&S Consumber Goods ( Germany) . Contract # GF- H/ET/G-95
2. Based on the most up-to-date stock situation, are there any risks of stockouts of key pharmaceuticals & health products at the central level in the next period of implementation? If yes, please comment. |  |  | No | No stock -outs are expected.
3. Comment on additional issues related to the procurement and supply management of pharmaceuticals and health products
During P2 PR has initiated regular monitoring on stocks and utilization of medicines and supplies by SRs. Based on these data PR can evaluate the requests coming from SRs critically and ask for additional justifications before agreeing on the amount of products requested. The information is crucial for better planning of next procurement rounds as well. PR is working on institutionalization of the Logistic Information System - warehouse database, namely PR logistic specialist is entering data regarding all procurements that took place since April, 2014. From May, 2015 SRs will be required to enter the utilization data on all products entered in the system. In order to get prepared for initiating first- line drug procurement by the government in 2015, the following activities were scheduled and initiated: 1. market research (ongoing) 2. meeting with local wholesalers and pharmaco companies’ representation offices (planned); 3. obtaining competitive prices by initiating direct negotiations with WHO prequalified manufacturers (planned); 4. negotiation with VPP and discussion on the opportunities to participate in the local tenders (ongoing). 5. providing results of these negotiations to the Ministry of Health (ongoing) . From the experience of P2 procurement, it takes a long time to get final, acceptable for tender regulations for quality product specifications from SRs that increases the lengh of procurment process. Exchange rate fluctuation may have a negative impact on the current procurement contracts for which the suppliers need to provide next deliveries according to the schedule (they may request rise in payment to cover the loss).

## PR_Cash Reconciliation_5A
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  | GEO-H-NCDC |  |  |  | ! A Statement of Sources and Uses of Funds (SSUF) is to be provided by PR along with the PUDR form
Progress Update - Reporting Period: |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 2
Currency: |  | EUR
Section 5: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update):
4030847.7715
Add: | 2. Cash received by the PR from the Global Fund during the period covered by this progress update: | [5 empty] | 0
| 3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update: | [5 empty] | 0
| 4. Interest received on bank account | [5 empty] | 0
| 5. Revenue from income-generating activities (if applicable) | [5 empty] | 0
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) | [5 empty] | 0 | 0
Less: | 7. Total cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): | [5 empty] | 2752053.64
| 8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign) | [5 empty] | -57049.4508
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) | [6 empty] | 2695004.1892
10. Cash Balance: End of period covered by Progress Update: | [7 empty] | 1335843.5823
Explanation of reconciliation adjustments (line 9)
! An explanation must be provided if there have been any adjustments.

## PR_Disbursement Request_5B
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  |  |  |  | GEO-H-NCDC
Progress Update - Reporting Period: |  |  |  |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  |  |  |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  |  |  |  | 2
Currency: |  |  | EUR
Section 5: Cash Reconciliation and Disbursement Request
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  |  |  | 2015-01-01 |  | end date: | 2015-12-31 |  | approved budget amount: | 11216378.6553 | forecasted amount: | 9246598.5561
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  |  |  | 2016-01-01 |  | end date: | 2016-03-31 |  | approved budget amount: |  | forecasted amount:
PR Total Forecast
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [12 empty] | 9246598.5561
cash "buffer" agreed with FPM (2) |  | Select
(cash "buffer") beginning date |  |  |  | 2016-04-01 |  | end date: |  |  | approved budget amount: |  | forecasted amount:
(1) Additional Cash buffer can be requested if the next PU/DR report will contain a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. An agreement in principal from the FPM should be obtained prior to requesting an additional cash buffer.
(2) When the additional (cash "buffer" ) period is 1 or 2 months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period | [7 empty] | "The variance resulted due to the following factors: The cost of services procured from SRs is less than budgeted due to tender procurement; The q-ties of products to be procured in 2015 were adjusted to the available stocks, AMC and target indicators; Considerable saving was made in second line ARV procurement considering the WHO recommendations regarding the simplification of ART regimens and related PSM and PPM costs were saved; Forecasted amount includes also payment for 2014 ARV procurement and related PSM and PPM costs and payment for December 2014 SRs service committed amounts IDA contract costs for condoms was adjusted to the actual amount; IDA order for syringes was adjusted to the stock available at GHRN, AMC and indicators; Saving is due to country's quota for methadone procurement also. Considering the high inflation rate the unit prices for procurement were not adjusted the last procurement lower prices and PSM unit cost was applied in calculation of forecast. Canceled activates cost (Opening of new ART center in Telavi and procurement of cars ) were deducted; Saving made in procurement of goods and services by PR was 186,750 EURO (the amount reflects difference between market prices and tedner costs and doesn't unclude cost of GSM servce which was joint TBand HIV program contract) without counting ARV cost the absorption rate is 60%
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from PR Cash Reconciliation sheet): | [10 empty] | 1335843.5823
| 4. Cash "in transit" disbursed to the PR: | [10 empty] | 438789
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR | [10 empty] | 0 | 1774632.5823
6. PR's Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [12 empty] | 7471965.9738
7. Does the PR's Disbursement Request include funds for health product procurement? | [7 empty] | Yes
8. Exchange Rate (used to translate local currency into grant currency) | [7 empty] | Name of local currency, date and source of the exchange rate, and other comments (if appropriate)
| - used to convert Opening Cash Balance |  |  |  |  | 2.415 |  | FX rate at the date of reporting (source: OANDA.com)
| - used to convert Closing Cash Balance |  |  |  |  | 2.2656 |  | Exchange rate at the closing reporting date (source: www.nbg.gov.ge)
| - used to convert Total Cash Outflow for the Progress Update Period |  |  |  |  | 0 |  | Exchange rate at the date of transaction (source: www.nbg.gov.ge)

## PR_Overall Performance_6
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | GEO-H-NCDC
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: | 2
Section 6: Overall Performance
A. PR's Overall Self-Evaluation of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The self-evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance.
The overall grant performance was considerably improved. The program indicator data for P2 clearly show greater achievements, especially for coverage indicators of key affected populations (FSWs, MSM). Great improvement was reported for coverage of PWIDs with NSP services (144% of the target number) that was a result of addition personnel hired (Mobile Ambulatory personnel was hired in advance to increase number of people working on outreach). Also, the changed principles of counting of coverage indicators in PF provided with GF implementation latter of January, 2015 much contributed to the performance improvement. There was important change regarding the supportive environment development for PWIDs in Georgia. Double Ministerial Decree (Minister of Health and Minister of Justice) was issued abolishing the requirement for medical doctors to report case of drug overdose to police. The decree will improve survival of PWIDs in case of overdose. For the most of the top 10 indicators the performance is either according to the plan (100% achievement) or the targets are overachieved. There is underachievement in coverage of FSWs and MSM with prevention package, but it has been considerably improved compared to P1. Along with changes in counting the coverage according to new PF, testing of PDI activities among MSM turned out to be more successful than among FSWs. Starting operation of LGBT resource centers should contribute to greater MSM coverage achievements in future also. Tanadgoma still needs to farther increase coverage to meet the targets set in P3 and P4. PR is working with Tanadgoma to address the critical issues regarding the coverage of FSWs in Telavi (Kakheti region) as the reported numbers are very low. There were sound achievements reported from National AIDS Center regarding the ART implementation. Monitoring and treatment of PLHIV were conducted considering the WHO recommendations of the ARV drugs quantification mission of June, 2014. The PQ was signed with MPP regarding the procurement of first and second line ARV drugs for 2015, but the payment will be made after delivery of medicines to the country in 2015. In December, 2014 Parliament of Georgia has approved the state budget law which includes the state obligation to provide 1,700,000 GEL for procurement of first line ARV drugs in 2015. The amount required for procurement of second line ARV drugs was recalculated based on the WHO recommended regimens which has resulted in considerable saving in the respective budget line and related PSM costs.PR is exploring different options for procurement of first line ARV drugs with the State Budget money, including local distributors and MPP in order to place the order on time and achieve procurement at lower possible price of quality medicines. Implementation of BSS and Size Estimation study among PWIDs has started late than planned as PR had to procure the service through electronic tender process. On September 30, the Relevant contract was signed with Curatio International Foundation for implementation of the surveys that will be finished in May, 2015 and PR will be able to provide the report to GF. Despite the fact that SRs are still using the excel based databases, the PR has achieved improved data reporting from SRs based on the continuous oversight and on-site instructions/validations regarding the ways of counting the indicators and the data-base improvement. In parallel, the PR is working on procurement of the service for unified HIV prevention database elaboration. The tender documentation is prepared and the announcement will be made in March, 2015. The service contracts are signed with SRs for 13 months, covering the period of December, 2014 and whole year 2015. The Tenders for Objective 1 are conducted and contracts are signed for the following activities: Strengthening of LBGT community; Strengthening of PLHIV community and training of HCWs on HIV related stigma and discrimination. Implementation will start in February and March of 2015. Market search was conducted for Media Campaign against stigma and discrimination. The tender will be announced in March, 2015. PR has initiated the monitoring of consumptions of health products by SRs and SSRs to assess the stocks and plan the future procurements based on the indicators and the consumption data to prevent both stock outs and expired products in stocks. Financial management: the two critical components of this work are a) external to Georgia - communication with the donor (GFATM), and b) internal to Georgia – communication and reporting with the Ministries of Health and Finance, with NCDC, state statistics department, tax authorities, state revenue service, suppliers, service providers, etc. The former is smooth and efficient, which helps the stable and robust operations. In 2014 PR has timely completed the submission of the first regular PU reporting also, met all of the donor’s additional ad-hoc requests on the provision of financial and/or operational data. This includes PR/SR end-of month balances/receivables/payables, grant fund receipts and payments to third parties, etc. Total receipt for 2014 was Eur 4,418K - one transfer from GFATM in Q2. Transition to state financial reporting was difficult process for SRs, especially for NGO SRs, but PR’s financial team was working with SRs on on-going basis for improvement of their accounting and reporting systems. RP operates bank account at the state treasury and accounting software ORIS (as an internal, albeit independent, part of NCDCs accounting), maintaining accurate and robust document filing for all transactions entered into either system. PR manages VAT smoothly, with the total worth of returnable VAT of GEL 64K; State Revenue Service has already registered these amounts on PR tax card, which is the prerequisite of its reimbursement shortly, as the technicalities are resolved by the same entity. PR paid total of Eur 2,752K to the vendors/providers during the current reporting period, whereas the total payments in 2014 constituted: Eur 3,127K. PR successfully procured one of the ‘Big Four’ companies (KPMG) as auditor (the contract was signed in 2015).
B. Planned Changes in the Program, if any
The opening of the new regional AIDS Center in Telavi (Kakheti region) was canceled due to the justification provided by the National AIDS Center. The main reason is that the new center willn't be cost-effective due to small number of HIV positive individuals living in that Geographic area. Although, there is no health care facility with infecions disease management profile that would serve as a SSR in the ART program componen
C. External factors beyond the control of the Principal Recipient that have impacted or may impact the Program

## PR_Cash Request_7A&B
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Georgia
Disease: | HIV/AIDS
Grant number: | GEO-H-NCDC
Principal Recipient: | NCDC
Program Start Date: | 2014-04-01
Currency: | EUR
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: | 2
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: | Cycle: | Annual | Number: | 2
Disbursement Request - Period Covered: | Beginning Date: | 2015-01-01 | End Date: | 2015-12-31
Disbursement Request - Number: | 2
Section 7: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from line 14 – “PR's Disbursement Request” in the tab “PR_Disbursement Request_4B”), in grant currency |  | 7471965.9738
2. Amount requested in words (in: EUR): |  | Seven millions four hundred seventy-one thousand nine hundred sixty-six
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Irma Khonelidze
Title: | Programme Director, GF PIU, NCDC
Date and Place: | 28/02/2015 Tbilisi, Georgia
NB: Please ensure that section 7C Bank Details on the following page is completed, if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.

## PR_Bank Details_7C
On-going Progress Update and Disbursement Request
NB: This page should be completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
7C: Bank Account Details
Disbursement Request Period
Summary
|  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: | NCDC | 5540395.9876
| Payee 2: | IDA Foundation | 198112.0645
| Payee 3: | PFSCM | 1733457.9218
| Payee 4: | 0 | 0
| Total |  | 7471965.9738 | The total does not match requested amount on PR signature page
Payee 1:
| Beneficiary Name: | NCDC |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds | EUR |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: | 5540395.9876 |  | Bank Account Number:
| Amount in Words: | Five millions five hundred forty thousand three hundred ninty six (EUR) |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | 1 |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) | 5540395.9876 |  | Bank Code (Other):
Routing Instructions:
Payee 2:
| Beneficiary Name: | IDA Foundation |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: | 240805.2144 |  | Bank Account Number:
| Amount in Words: | One hundred nintyeight thousand one hundred twelve (EUR) |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | 1.2155 |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) | 198112.0645 |  | Bank Code (Other):
Routing Instructions:
Payee 3:
| Beneficiary Name: | PFSCM |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds | USD |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: | 2107018.1039 |  | Bank Account Number:
| Amount in Words: | One million seven hundred thirtythree thousand four hundred fiftyeight (EUR) |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | 1.2155 |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) | 1733457.9218 |  | Bank Code (Other):
Routing Instructions:
Payee 4:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Note on C61: User: Assumed FX rate of 31.12.2014 from OANDA.com

## Checklist
List of supporting documents for PU/DR review
This checklist is included for information and not for completion.
List of Latest Approved Documents by functional area | To be made available to the LFA by the PR | To be submitted by the LFA to the Secretariat | Comments
M&E
Performance Framework | x
M&E Plan | x
Survey results | x |  | For Impact/Outcome indicators
M&E Systems Strengthening Assessment | x |  | If newly available during the reporting period.
Other M&E assessments done by partners to assess data quality and M&E system issues. | x |  | If newly available during the reporting period.
Procurement
Consumption reports for pharmaceuticals and health products | x
Supplier invoices | x
PSM Plan | x
Stock level reports | x
Finance
Approved budgets | x |  | For the periods covered by Progress Update and Disbursement Request, including the buffer period.
Statement of sources and uses of funds (Cash flow statement) | x | x | See guidance on SSUF content and format in the guidelines.
Cash books | x
General Ledger | x
Cash forecasts | x
Bank statements | x
Bank Reconciliations | x
Annual PR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x | x
Annual SR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x
General Management
Grant Agreement (including Annex A and subsequent implementation letters) | x
Workplan | x

## LFA_Programmatic Progress_1A
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  | Georgia
Disease: |  | HIV/AIDS
Grant Number: |  | GEO-H-NCDC
Principal Recipient: |  | NCDC
Program Start Date: |  | 2014-04-01
Currency: |  | EUR
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 2
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2015-01-01 | End Date: | 2015-12-31
Disbursement Request - Number: |  | 2
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators | [12 empty] | A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results | Verification Method | Verified Result | LFA comments on (a) verified result, (b) source of information used by the PR to report results, including the status of completion of surveys and other methods to measure Impact/Outcome, as applicable, | Impact / Outcome | Indicator Description | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results
Impact | Percentage of men who have sex with men who are living with HIV |  |  |  | 2015 | 15 | 2016-02-15 | n/a | BSS (Behavioral and Surveillance Survey) |  |  |  | Impact | Percentage of men who have sex with men who are living with HIV | 2015 | 15 | 42415 | n/a | BSS (Behavioral and Surveillance Survey)
Impact | Percentage of people who inject drugs who are living with HIV |  |  |  | 2014 | 3 | 2015-02-15 | n/a | BSS (Behavioral and Surveillance Survey) |  |  |  | Impact | Percentage of people who inject drugs who are living with HIV | 2014 | 3 | 42050 | n/a | BSS (Behavioral and Surveillance Survey)
Impact | Percentage of sex workers who are living with HIV |  |  |  | 2014 | 2.3 | 2015-02-15 | 0.007 | BSS (Behavioral and Surveillance Survey) |  |  |  | Impact | Percentage of sex workers who are living with HIV | 2014 | 2.3 | 42050 | 0.007 | BSS (Behavioral and Surveillance Survey)
Impact | AIDS related mortality per 100,000 population |  |  |  | 2014 | 2.3 | 2015-02-15 | 2.1 | HMIS |  |  |  | Impact | AIDS related mortality per 100,000 population | 2014 | 2.3 | 42050 | 2.1 | HMIS
Outcome | Percentage of adults and children with HIV known to be on treatment 12 months after initiation of antiretroviral therapy. |  |  |  | HMIS | 0.86 | 2016-02-15 | 0.87 | HMIS |  |  |  | Outcome | Percentage of adults and children with HIV known to be on treatment 12 months after initiation of antiretroviral therapy. | HMIS | 0.86 | 42415 | 0.87 | HMIS
Outcome | Percentage of men reporting the use of a condom the last time they had anal sex with a male partner |  |  |  | BSS (Behavioral Surveillance Survey) | 0.75 | 2016-02-15 | n/a | BSS (Behavioral and Surveillance Survey) |  |  |  | Outcome | Percentage of men reporting the use of a condom the last time they had anal sex with a male partner | BSS (Behavioral Surveillance Survey) | 0.75 | 42415 | n/a | BSS (Behavioral and Surveillance Survey)
Outcome | Percentage of sex workers reporting the use of a condom with their most recent client |  |  |  | BSS (Behavioral Surveillance Survey) | 0.92 | 2015-02-15 | 0.9 | BSS (Behavioral and Surveillance Survey) |  |  |  | Outcome | Percentage of sex workers reporting the use of a condom with their most recent client | BSS (Behavioral Surveillance Survey) | 0.92 | 42050 | 0.9 | BSS (Behavioral and Surveillance Survey)
Outcome | Percentage of people who inject drugs reporting the use of sterile injecting equipment the last time they injected |  |  |  | BSS (Behavioral Surveillance Survey) | 0.84 | 2015-02-15 | n/a | BSS (Behavioral and Surveillance Survey) |  |  |  | Outcome | Percentage of people who inject drugs reporting the use of sterile injecting equipment the last time they injected | BSS (Behavioral Surveillance Survey) | 0.84 | 42050 | n/a | BSS (Behavioral and Surveillance Survey)
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
[5 empty] | - | - | - | - | Select | [5 empty] | - | - | - | - | Select
Formulas:
Report Due Date = [Report Due Date]

## LFA_Programmatic Progress_1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  |  | GEO-H-NCDC
Progress Update - Reporting Period: |  |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  |  | 2
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators | [15 empty] | B. Programmatic Indicators
Objective No. | Indicator No. | Indicator Description |  |  |  |  | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR) | Verification Method | Verified Result | % achievement (Please calculate as appropriate) | LFA analysis on progress to date and any variance between targets and results, and any other comments (this should not be a “Copy and Paste” of the reasons provided by the PR) | Objective No. | Indicator No. | Indicator Description | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR)
2 | 1 | Number of MARPs (IDUs, MSM and FSWs) covered with HIV testing and counselling (including provision of results) |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 14298 | 12637 |  |  |  |  | 2 | 1 | Number of MARPs (IDUs, MSM and FSWs) covered with HIV testing and counselling (including provision of results) | Current grant | N-not cumulative | Yes - Top 10 | 14298 | 12637
2 | 1.1. | Number of prisoners covered with VCT (HIV testing and counselling, including provision of results) |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 2850 | 2388 |  |  |  |  | 2 | 1.1. | Number of prisoners covered with VCT (HIV testing and counselling, including provision of results) | Current grant | N-not cumulative | Yes - Top 10 | 2850 | 2388
2 | 1.2 | Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 0.89 | 0.911 |  |  |  |  | 2 | 1.2 | Proportion of new individuals who test positive for HIV, enrolled in care (pre-ART or ART) services | Current grant | N-not cumulative | Yes - Top 10 | 0.89 | 0.911
2 | 2.1 | Number and percentage of MSM reached with HIV prevention programmes - defined package of services |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 8% (1428/17000) | 6.4%(1087/17000) |  |  |  |  | 2 | 2.1 | Number and percentage of MSM reached with HIV prevention programmes - defined package of services | Current grant | N-not cumulative | Yes - Top 10 | 8% (1428/17000) | 6.4%(1087/17000)
2 | 2.2 | Number and percentage of IDUs reached with HIV prevention programmes - defined package of services |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 40% (17925/45000) | 57% (25838/45000) |  |  |  |  | 2 | 2.2 | Number and percentage of IDUs reached with HIV prevention programmes - defined package of services | Current grant | N-not cumulative | Yes - Top 10 | 40% (17925/45000) | 57% (25838/45000)
2 | 2.3 | Number and percentage of FSWs reached with HIV prevention programmes - defined package of services |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 19% (1232/6500) | 16.1% (1044/6500) |  |  |  |  | 2 | 2.3 | Number and percentage of FSWs reached with HIV prevention programmes - defined package of services | Current grant | N-not cumulative | Yes - Top 10 | 19% (1232/6500) | 16.1% (1044/6500)
2 | 2.4 | Percentage of individuals receiving OST who received treatment for at least 6 months |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 450 | 503 |  |  |  |  | 2 | 2.4 | Percentage of individuals receiving OST who received treatment for at least 6 months | Current grant | N-not cumulative | Yes - Top 10 | 450 | 503
2 | 2.5 | Percentage of key affected population screened for TB |  |  |  |  | Current grant | N-not cumulative | No | 40% (3002/7503) | 36% (2673/7503) |  |  |  |  | 2 | 2.5 | Percentage of key affected population screened for TB | Current grant | N-not cumulative | No | 40% (3002/7503) | 36% (2673/7503)
3 | 3 | Number and percentage of eligible adults and children currently receiving antiretroviral therapy |  |  |  |  | Current grant | N-not cumulative | Yes - Top 10 | 60.0%(2740/4570) | 55% (2590/4570) |  |  |  |  | 3 | 3 | Number and percentage of eligible adults and children currently receiving antiretroviral therapy | Current grant | N-not cumulative | Yes - Top 10 | 60.0%(2740/4570) | 55% (2590/4570)
3 | 3.1 | Percentage of adults and children that initiated ART, with an undetectable viral load at 12 months (<1000 copies/ml) |  |  |  |  | Current grant | Y-cumulative annually | No | 0.83 | 0.815 |  |  |  |  | 3 | 3.1 | Percentage of adults and children that initiated ART, with an undetectable viral load at 12 months (<1000 copies/ml) | Current grant | Y-cumulative annually | No | 0.83 | 0.815
3 | 3.2 | Number of patients with HIV Hep C co-infection receiving Hep C treatment |  |  |  |  | Current grant | Y-cumulative annually | No | 150 | 136 |  |  |  |  | 3 | 3.2 | Number of patients with HIV Hep C co-infection receiving Hep C treatment | Current grant | Y-cumulative annually | No | 150 | 136
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
C LFA comments on data quality and reporting issues (!) This section should contain any common issues and/or additional information related to data quality and reporting on the programmatic indicators which are not covered in 'LFA analysis on progress to date and any variance between targets and results'

## LFA_Grant Management_2
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | GEO-H-NCDC
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: | 2
Section 2: Grant Management
A. PR & LFA COMMENTS ON THE FULFILLMENT OF OUTSTANDING CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! This table should contain a full text of the CP and/or other special conditions due for fulfilment during this period or outstanding from previous periods.
! Some Special Conditions may apply to more than one period of grant implementation. Their fulfilment during one period does not automatically imply fulfilment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
! If a Condition Precedent that was previously fulfilled is re-opened due to new circumstances, and the issue addressed by this condition is considered critical, the issue should be disclosed by the LFA in the Section 4 LFA Findings and Recommendations. At the discretion of the Fund Portfolio Manager, the issue may be followed up through the management actions assigned by the Global Fund to the PR.
|  | PR SECTION | LFA SECTION
Conditions Precedent and/or other special conditions |  | Status | Status | Analysis (this should not be a "Copy and Paste" of the comments provided by the PR)
1. Conditions Precedent to the First Disbursement (Terminal Date as stated in block 7A of the Face Sheet): The first disbursement of Grant funds by the Global Fund to the Principal Recipient is subject to: a) the Principal Recipient entering into temporary arrangements with the existing Sub- recipients carrying out Program activities, under grant number GEO-H-GPIC, until the Principal Recipient submits a request for tender in accordance with the laws of Georgia, and new Sub-recipients are selected through such tender (for the avoidance of doubt, during such temporary arrangements period, the Standard Terms and Conditions of this Agreement shall apply); |  | Met
The first disbursement of Grant funds by the Global Fund to the Principal Recipient is subject to: b) delivery by the Principal Recipient to the Global Fund, in form and substance satisfactory to the Global Fund, of a letter signed by the Authorized Representative of the Principal Recipient setting forth the name, title and authenticated specimen signature of each person authorized to sign disbursement requests under Article 10 of the Standard Terms and Conditions of this Agreement and, in the event a disbursement request may be signed by more than one person, the conditions under which each may sign. |  | Met
2. Condition Precedent to the Use of Grant Funds by the Principal Recipient for procurement of health and non-health products (Terminal Date as stated in block 7B of the Face Sheet): The use of Grant funds by the Principal Recipient for procurement of health and non-health products is subject to delivery by the Principal Recipient to the Global Fund, each in form and substance satisfactory to the Global Fund, of an Operations Manual (OM) which shall include procedures in respect of Procurement and Supply Management and regular progress updates, and shall address weaknesses identified by the Principal Recipient assessment, including but not limited to the following: a) Standard Operating Procedures (SOPs) for procurement of health and non-health products; and b) SOPs for supply chain management (including management information systems, forecasting and quantification, storage and distribution) of health products and pharmaceuticals on a national level (from central level to patient level). Notwithstanding the foregoing set forth in this Section B(2)(b), prior to the satisfaction of this condition precedent, the Principal Recipient may use Grant funds, with the prior written approval of the Global Fund, for procurement of non-health products. |  | Met
3. Conditions Precedent to disbursement by the Global Fund to the Principal Recipient or use by the Principal Recipient of Grant funds to finance activities related to Objective 1: The Global Fund and the Principal Recipient shall agree on the list of activities related to Objective 1 |  | Met
4. Condition Precedent to disbursement by the Global Fund to the Principal Recipient or use by the Principal Recipient of Grant funds for the 2015 budget: a) No later than 14 August 2014, the Ministry of Labour, Health and Social Affairs shall inform the Global Fund of the HIV treatment protocol that will be used in Georgia during the current implementation period; upon which the Global Fund will determine its ART funding contribution which would be incorporated into the 2015 budget (the Global Fund reserves a right to limit the ART funding to the treatment regimens recommended in the WHO 2013 treatment guidelines). |  | Met
4. Condition Precedent to disbursement by the Global Fund to the Principal Recipient or use by the Principal Recipient of Grant funds for the 2015 budget: b) By no later than 30 September 2014, revision by the Principal Recipient of the 2015 budget and Performance Framework targets for key populations, which shall further optimize and incorporate the results of: i) the population size estimates conducted between 1 January to 31 July 2014. and; ii) the Budgeted Sustainability Plan pursuant to Section C(2) of this Annex A (June 30, 2014) The date was postponed by GF with IL1 to 31,January,2015. |  | Met
SPECIAL TERMS AND CONDITIONS FOR THIS AGREEMENT No later than 30 June 2014, the CCM shall, or the Principal Recipient shall cause the CCM to, submit a Budgeted Sustainability Plan for the gradual governmental take-over of financing, starting in 2015, for activities supported by this Grant. GF agreed to postpone the terminal date of the condition to 31 January, 2015 |  | Met
At its sole discretion, the Global Fund reserves the right to require the principal recipient to use the services of a suitability qualified procurement agent for the procurement of designated list of health products, including pharmaceuticals, for reasons of quality, and or value for money. when invoking this right, the Global Fund will stipulate the list of health products |  | Met
Select
Select
Select
Select
Select
Select
B. PR & LFA REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! This table should contain all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress.
Global Fund Management Actions |  | LFA Review of PR Progress on Global Fund Management Actions
Financial management and systems During revision of the Work plan and Budget it has been noted that the PR tends to modify the budget under negotiation on ongoing basis. This practice has created a confusion, as there was a difference in multiple versions submitted to the Secretariat. Additionally it has resulted in CT's considerable time for verification, clarifications, and unnecessary communication. Action Required: The budget approved by the Global Fund should be treated as a plan, and should not be changed on an ongoing basis. The re-programming requests should be approved by Global Fund through the official request, and variance between the originally approved budget and re-allocations should be reported as part of the EFR
Qpioid Substitution Program While the overall achievement of the OST indicator does not raise questions, our further discussions have revealed that OST patients are transferred from the State Program to the GF Program by the State Program officials due to inability of patients to cover the co-payment requested by the state program or difficulties to manage patients with some mental problems. Since the movements of the patients are controlled by the State Program, and currently free treatment is provided by the Global Fund, the move of the patients to the Global 'Fund program for the above mentioned reasons is understandable. However, it raises an ethical issue of continuation of the treatment for the most disadvantaged group, when the Global Fund discontinues the OST activities in Georgia. In view of the above, we strongly recommend that the PR causes the CCM, as part of the sustainability plan, to initiate discussions on the future adoption of the co-payment waver policy for disadvantaged OST patients, or find any other appropriate solutions, for gradual inclusion of the GF program OST patients into the state program.
Issue: During the review, it was noted that the SRs have experienced stock outs in condoms, lubricants due to the late procurement by the previous PRoFurthermore, the Global Fund Secretariat is aware of the complexity of the regulations and the processes of the State Procurement Agency, which may potentially result in delayed procurement of drugs and stock outs. Action required: The PR should continue to update the Global Fund on the progress made with respect to the procurement of drugs and health products and to continue to monitor the process. While the Global Fund Secretariat acknowledges the efforts made by the PR to streamline the processes, the PR is requested to continue to follow up and ensure that the orders are placed in timely manner and the buffer period is included in the calculations, in order to avoid stock out of medicines and health products and interruption of services.
During the PHPM review of the TB and HIV Grants conducted in July 2014, the Global Fund has provided set of recommendations on the issues identified in 27 sites. The PR submitted a consolidated feedback on 11h of October 2014 including proposed measures to address the issues identified as well as updated the Global Fund on the progress made with respect to completion and implementation of the Maintenance and Service Plan for health procurement under the Global Fund grants. We appreciate the PR's efforts so far. Please be informed that we will be conducting a follow up mission to review the progress on the implementation of the Maintenance and Service Plan.
We recognize that the PIU has been established several months ago, and the staff needs sufficient time to learn and adapt to the requirements of the Global Fund. However, taking into consideration the capacity building opportunities provided by the GF and GMS, it is expected that less iterations should take place for the key grant documents (revised Budget and Work plan, PSM related documents, and Performance Framework) prepared by the PRoWe do hope to see more progress in the future.
C. PR & LFA COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
This table should contain the due date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
| PR SECTION |  | LFA SECTION
Required Documentation | Due date | Status | Due date | Status | Comments
PR Audit Report | 2015-03-31 | Select
Enhanced Financial Reporting (EFR) | 2015-02-28 | Select

## LFA_Total PR Cash Outflow_3A
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | GEO-H-NCDC
Progress Update - Reporting Period: | Cycle: | Semester |  | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 |  | End Date: | 2014-12-31
Progress Update - Number: | 2
Currency: | EUR
Section 3A: Total PR Cash Outflow
LFA-VERIFIED TABLES ON TOTAL PR CASH OUTFLOW
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance | All amounts are in: | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
1. Total cash outflow vs. budget | 3370173.8693 | 2752053.64 | 618120.2293 |  |  | 6365135.8508 | 3127372.9291 | 3237762.9217 |  | 1. Total cash outflow vs. budget | 3370173.8693 | 2752053.64 | 618120.2293 |  | 6365135.8508 | 3127372.9291 | 3237762.9217
1a. PR's total expenditures | 1512380.6546 | 990032.05 | 522348.6046 |  |  | 3553454.3749 | 1006122.6851 | 2547331.6898 |  | 1a. PR's total expenditures | 1512380.6546 | 990032.05 | 522348.6046 |  | 3553454.3749 | 1006122.6851 | 2547331.6898
1b. Disbursements to sub-recipients | 1857793.2147 | 1762021.59 | 95771.6247 |  |  | 2811681.4759 | 2121250.244 | 690431.2319 |  | 1b. Disbursements to sub-recipients | 1857793.2147 | 1762021.59 | 95771.6247 |  | 2811681.4759 | 2121250.244 | 690431.2319
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance |  | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
2. Pharmaceuticals & health product expenditures vs. budget | 1051878.3797 | 842595.3534 | 209283.0263 |  |  | 2883695.7433 | 842595.3534 | 2041100.3899 |  | 2. Pharmaceuticals & health product expenditures vs. budget | 1051878.3797 | 842595.3534 | 209283.0263 |  | 2883695.7433 | 842595.3534 | 2041100.3899
2a. Medicines and pharmaceutical products | 1040162.365 | 169300.0424 | 870862.3226 |  |  | 1150424.2441 | 169300.0424 | 981124.2017 |  | 2a. Medicines and pharmaceutical products | 1040162.365 | 169300.0424 | 870862.3226 |  | 1150424.2441 | 169300.0424 | 981124.2017
2b. Health products and health equipment | 11716.0147 | 673295.311 | -661579.2963 |  |  | 1733271.4992 | 673295.311 | 1059976.1882 |  | 2b. Health products and health equipment | 11716.0147 | 673295.311 | -661579.2963 |  | 1733271.4992 | 673295.311 | 1059976.1882
* If LFA-entered data differs from PR's figures, the respective cells will change colour automatically
3. Indicate any expenditures (incurred or forecasted) that should not be financed by the Global Fund

## LFA_EFR Review_3B
LFA review of Enhanced Financial Reporting template
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Georgia
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | GEO-H-NCDC
Principal Recipient: |  |  | NCDC
Program Start Date: |  |  | 2014-04-01
Currency: |  |  | EUR
Section 3B: ENHANCED FINANCIAL REPORTING PERIOD
Current Period |  |  | Beginning Date: | End Date:
Cumulative Period |  |  | Beginning Date: | End Date:
1. CHECKLIST
The following information provided by the Principal Recipient in its EFR has been checked. |  |  |  |  | Comments if any:
| Select | The template has been fully completed.
1
| Select | The total figures in Tables A, B and C are equal.
2
| Select | The reporting dates are correct for both current period and cumulative period.
3
| Select | The total budget figure is accurate based on existing approved budgets.
4
| Select | The PR expenditure in Table C is consistent with PR expenditure for the same period as provided in the Progress Updates/Disbursements Request (PU/DR).
5
| Select | The total expenditure is supported by appropriate documentation ( PR expenditure reports, bank reconciliations, SR expenditure reports to PR etc.) or reasonable assumptions.
6
2. COMPLETION OF THE TEMPLATE
Comments on the process, assumptions and supporting documentation used by the PR to complete the template. (If space is insufficient, please provide comments in an addendum)
3. VARIANCE ANALYSIS
Comments on the explanations for variances provided by the PR (LFA can also provide comment directly on the EFR template completed by the PR)
Signed on behalf of the LFA:
Name:
Title:
Date and Place:

## LFA_Procurement Info_4
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | GEO-H-NCDC
Progress Update - Reporting Period: | Cycle: | Semester |  | Number: |  | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 |  | End Date: |  | 2014-12-31
Progress Update - Number: | 2
Section 4: LFA-verified Procurement and Supply Management Information
| PR's response | LFA's response | LFA Comments/Analysis
1a. Has the PR updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? (If health products procurement information has not been entered into the PQR, please explain why in comments box) | Yes | Select
1b. Value of Pharmaceuticals and Health Products in the PQR (6 categories only)
(!) This table is included in the PU/DR form with the aim to improve completeness of information in the PQR system and not for comparing PQR amounts vis-à-vis expenditure per se. NB: PQR and expenditure amounts on health products may not be equal due to a timelag between payments and delivery of pharmaceuticals/health products. (!) For further guidance on PQR data entry, please refer to the guidelines.
Reporting Currency
PQR Product Categories | Value of products received during reporting period | Value of products entered by the PR and verified as correct by the LFA in the PQR during reporting period | Variance | Reason for Variance | Cumulative value of products received since Jan 2011 | Cumulative value of products verified as correct by the LFA in the PQR since Jan 2011 | Variance | Reason for Variance
1. Anti-malaria medicines
2. Bed nets
3. Rapid Diagnostic Tests
4. Condoms
5. Anti-retrovirals
6. Anti-TB Medicines
Total | 0 | 0 | 0 |  | 0 | 0 | 0
2. Based on best information available to the LFA, are there any risks of drug stockout at the central level in the next period of implementation? (If yes, please explain in comments box) ! This section should be completed by the LFA based on best information on stock levels at the central level available to the LFA and should not require dedicated visits for on-site checks of stocks. | No | Select
3. PR comments on issues related to the procurement and supply management of pharmaceuticals and health products |  |  |  | LFA analysis on issues related to the procurement and supply management of pharmaceuticals and health products
During P2 PR has initiated regular monitoring on stocks and utilization of medicines and supplies by SRs. Based on these data PR can evaluate the requests coming from SRs critically and ask for additional justifications before agreeing on the amount of products requested. The information is crucial for better planning of next procurement rounds as well. PR is working on institutionalization of the Logistic Information System - warehouse database, namely PR logistic specialist is entering data regarding all procurements that took place since April, 2014. From May, 2015 SRs will be required to enter the utilization data on all products entered in the system. In order to get prepared for initiating first- line drug procurement by the government in 2015, the following activities were scheduled and initiated: 1. market research (ongoing) 2. meeting with local wholesalers and pharmaco companies’ representation offices (planned); 3. obtaining competitive prices by initiating direct negotiations with WHO prequalified manufacturers (planned); 4. negotiation with VPP and discussion on the opportunities to participate in the local tenders (ongoing). 5. providing results of these negotiations to the Ministry of Health (ongoing) . From the experience of P2 procurement, it takes a long time to get final, acceptable for tender regulations for quality product specifications from SRs that increases the lengh of procurment process. Exchange rate fluctuation may have a negative impact on the current procurement contracts for which the suppliers need to provide next deliveries according to the schedule (they may request rise in payment to cover the loss).

## LFA_Findings&Recommendations
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | GEO-H-NCDC
Progress Update - Reporting Period: | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: | 2
LFA-specific section: LFA Findings & Recommendations
! Based on the information provided in the previous sections and your understanding of the grant, please summarise any important management issues, proposing a recommendation for each. NB: an issue is considered as 'important' if it impacts or is likely to impact program implementation and results. ! Instead of repeating detailed descriptions of issues covered in other sections, it is acceptable to state the issue and reference the section containing the details.
Functional Areas | Description of Identified Issues (in order of importance) |  |  | LFA Recommendations (in order of importance) | FPM Comments (to be completed upon receipt of the LFA-verified form)
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
LFA_Findings & Recommendations
Select
Yes
No
Select
Program management (including SR management)
Financial management and systems
Monitoring and evaluation
Pharmaceutical & health product management
Other management issues, including: PR capacity to develop quality programmatic and financial reports

## LFA_Cash Reconciliation_5A
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | GEO-H-NCDC
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2015-01-01 | End Date: | 2015-12-31
Disbursement Request - Number: |  | 2
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
A. LFA-VERIFIED CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
|  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments on verified amounts (if they are different from those reported by the PR) and PR's explanation of reconciliation adjustments (line 9)
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update): |  |  |  | 4030847.7715
Add: |  |  |  | 0
2. Cash received by the PR from the Global Fund during the period covered by this progress update: (1)
| 3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update: (1) |  |  | 0
| 4. Interest received on bank account |  |  | 0
| 5. Revenue from income-generating activities (if applicable) |  |  | 0
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) |  |  | 0
Less: | 7. Total PR cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): |  |  | 2752053.64
| 8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | -57049.4508
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | 0
10. Cash Balance: End of period covered by Progress Update: |  |  |  | 1335843.5823 | 0

## LFA_Disbursement Recommend_5B
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | GEO-H-NCDC
Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2015-01-01 | End Date: | 2015-12-31
Disbursement Request - Number: |  | 2
Currency: |  | EUR
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
B. LFA-RECOMMENDED DISBURSEMENT AMOUNT AND EXPLANATIONS
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  | 2015-01-01 | end date: | 2015-12-31 |  | Approved budget amount (reported by PR): |  | 11216378.6553 | Forecasted amount (reported by PR): | 9246598.5561
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount:
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  | 2016-01-01 | end date: | 2016-03-31 |  | Approved budget amount (reported by PR): |  | 0 | Forecasted amount (reported by PR): | 0
PR Total Forecast
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount: |  | 9246598.5561
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [10 empty] | LFA Total Forecast
0
(cash "buffer") beginning date |  | 2016-04-01 | end date: |  |  | approved budget amount: |  | 0 | forecasted amount: | 0
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount:
(1) Upon agreement with the FPM, additional Cash buffer can be requested if the PU/DR report contains a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. However such requests may or may not be satisfied based on the review of the current PUDR
(2) When the additional (cash "buffer" ) period is 1 or 2months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
PR's explanation of any significant variance between forecasted amounts and amounts as originally budgeted. |  |  | "The variance resulted due to the following factors: The cost of services procured from SRs is less than budgeted due to tender procurement; The q-ties of products to be procured in 2015 were adjusted to the available stocks, AMC and target indicators; Considerable saving was made in second line ARV procurement considering the WHO recommendations regarding the simplification of ART regimens and related PSM and PPM costs were saved; Forecasted amount includes also payment for 2014 ARV procurement and related PSM and PPM costs and payment for December 2014 SRs service committed amounts IDA contract costs for condoms was adjusted to the actual amount; IDA order for syringes was adjusted to the stock available at GHRN, AMC and indicators; Saving is due to country's quota for methadone procurement also. Considering the high inflation rate the unit prices for procurement were not adjusted the last procurement lower prices and PSM unit cost was applied in calculation of forecast. Canceled activates cost (Opening of new ART center in Telavi and procurement of cars ) were deducted; Saving made in procurement of goods and services by PR was 186,750 EURO (the amount reflects difference between market prices and tedner costs and doesn't unclude cost of GSM servce which was joint TBand HIV program contract) without counting ARV cost the absorption rate is 60%
LFA's explanation of any significant variance between forecasted amounts and amounts as originally budgeted. Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from LFA or PR Cash Reconciliation sheet): |  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments
[5 empty] | 1335843.5823 | 0
| 4. Cash "in transit" disbursed to the PR: |  |  |  | 438789
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR : |  |  |  | 0
[5 empty] | PR-requested amount | LFA-recommended amount
6. Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): |  |  |  |  | 7471965.9738 | 0
7. Does the PR's Disbursement Request include funds for health product procurement? |  |  |  |  | Select
8. Exchange Rate (used to translate local currency into grant currency)
|  | Rates used by the PR | LFA-verified rates |  | Name of local currency and LFA comments on the exchange rates used by the PR
| - used to convert Opening Cash Balance | 2.415
| - used to convert Closing Cash Balance | 2.2656
| - used to convert Total PR Cash Outflow for the Progress Update Period | 0

## LFA_Overall Performance_6
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | GEO-H-NCDC
Progress Update - Reporting Period: |  | Cycle: | Semester | Number: | 2
Progress Update - Period Covered: |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 2
Section 6: LFA EVALUATION AND COMMENTS ON OVERALL PERFORMANCE
A. Overall Evaluation and Rating of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance on the completion of this section. ! For RCC grants, this section should cover the period from the RCC start date through the end date of the current Progress Update period. ! For guidance on the methodology for rating overall performance, refer to Annex 2 of Guidelines.
Indicator rating | Select |  | Any major management issues resulting in downgrade? | Select |  | Overall Grant Rating | Select
B. LFA comments on PR planned changes in the program, if any
C. LFA Comments on External Factors Beyond Control of the Principal Recipients that have impacted or may impact program

## LFA_DisbursementRecommendation7
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Georgia
Disease: |  |  | HIV/AIDS
Grant Number: |  |  | GEO-H-NCDC
Principal Recipient: |  |  | NCDC
Program Start Date: |  |  | 2014-04-01
Currency: |  |  | EUR
PROGRESS UPDATE PERIOD | [7 empty] | DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Semester | Number: | 2 |  | Disbursement Request - Disbursement Period: |  | Cycle: | Annual | Number: | 2
Progress Update - Period Covered: |  |  | Beginning Date: | 2014-07-01 | End Date: | 2014-12-31 |  | Disbursement Request - Period Covered: |  | Beginning Date: | 2015-01-01 | End Date: | 2015-12-31
Progress Update - Number: |  |  | 2 |  |  |  |  | Disbursement Request - Number: |  | 2
Section 7: Disbursement Recommendation
A. DISBURSEMENT RECOMMENDATION
| Overall Rating | Select
Indicative disbursement ranges by performance rating (included as a reference)
Performance rating |  |  | Range for cumulative disbursement amount (after the currently recommended disbursement)
A1 | Exceeding expectations |  | Above 95% of cumulative budget through the next reporting period
A2 | Meeting expectations |  | Between 85-105% of cumulative budget through the next reporting period
B1 | Adequate |  | Between 55-95% of cumulative budget through the next reporting period
B2 | Inadequate but potential demonstrated |  | Between 25-65% of cumulative budget through the next reporting period
C | Unacceptable |  | Below 35% of cumulative budget through the next reporting period
1. Cash amount requested by the Principal Recipient from the Global Fund for next disbursement period plus one additional quarter (amount in: EUR): | [6 empty] | 7471965.9738 |  | Seven millions four hundred seventy-one thousand nine hundred sixty-six
2. LFA disbursement recommendation (amount in: EUR): | [6 empty] | 0
State the amount in words
Cumulative budget through the next period of implementation (including the buffer) |  |  | Cumulative disbursed amount to date (*) |  | Cumulative disbursed after recommended disbursement (including the buffer) |  | % range |  | Is the recommended disbursement within the range?
| 6365135.8508 |  |  |  | 0 |  | 0% |  | Select
(*)This data can be obtained from the "Disbursements in detail report (PDF)" (http://www.theglobalfund.org/documents/disbursementdetails.pdf)
3. Rationale for the LFA's disbursement recommendation (if resulting in cumulative disbursement outside the indicative ranges):
B. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [8 empty] | Comments regarding verifications, if any:
| Select | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request
| Select | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable).
| Select | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement).
| Select | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress.
| Select | Exchange rate stated by Principal Recipient has been verified and is correct.
| Select | PR Bank details verified/corrected by LFA
| Select | Current budget forecasts of the Principal Recipient for the next disbursement period plus buffer period have been reviewed for reasonableness
| Select | LFA has debriefed the Principal Recipient on the key findings (comment on the format of this debriefing)
NB: Please ensure that section 7C Bank Details on the following page is completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
D. Summary of the LFA's approach used for verification of financial, programmatic and procurement data and Quality Assurance undertaken by the LFA
In this section the LFA should indicate, as applicable, what percentage of expenditures was verified at PR level, if any expenditures were verified at SR level, how many site visits were made, what tender documentation was verified, and any other material parts of verification procedures in line with the verification approach agreed upfront between the LFA and GF Secretariat based on country/grant risks. As a good practice, the verification approach needs to be reviewed jointly by the LFA and the Secretariat annually.
NB: The LFA should sign a printed version of the verified PU/DR and send it to the Secretariat as a pdf file by email, or include an electronic signature in the Excel file to be submitted to the Global Fund.
Signed on behalf of the LFA:
Name:
Title:
Date and Place:

## LFA_Bank Details_7C
LFA On-going Progress Review and Disbursement Recommendation
Note for LFAs: This page should be completed by the PR if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement. The amounts and bank details below are displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
7C: LFA-verified Bank Account Details
| Disbursement Request Period | #REF!
| Summary |  |  |  |  | Summary
|  | Beneficiary Name | Amount in grant currency |  |  |  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: | #REF! | #REF! |  |  | Payee 1 - Principal Recipient: | #REF! | #REF!
| Payee 2: | #REF! | #REF! |  |  | Payee 2: | #REF! | #REF!
| Payee 3: | #REF! | #REF! |  |  | Payee 3: | #REF! | #REF!
| Payee 4: | #REF! | #REF! |  |  | Payee 4: | #REF! | #REF!
| Total |  | #REF! | #REF! |  | Total |  | #REF! | #REF!
| Payee 1: |  |  |  |  | Payee 1:
| Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF! | Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF!
| Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF! | Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF!
| Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF! | Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF!
| Amount in Words: | #REF! |  | Bank Address | #REF! | Amount in Words: | #REF! |  | Bank Address | #REF!
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF! | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF!
| Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF! | Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF!
|  |  |  | Routing Instructions: | #REF! |  |  |  | Routing Instructions: | #REF!
| Payee 2: |  |  |  |  | Payee 2:
| Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF! | Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF!
| Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF! | Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF!
| Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF! | Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF!
| Amount in Words: | #REF! |  | Bank Address | #REF! | Amount in Words: | #REF! |  | Bank Address | #REF!
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF! | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF!
| Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF! | Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF!
|  |  |  | Routing Instructions: | #REF! |  |  |  | Routing Instructions: | #REF!
| Payee 3: |  |  |  |  | Payee 3:
| Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF! | Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF!
| Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF! | Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF!
| Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF! | Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF!
| Amount in Words: | #REF! |  | Bank Address | #REF! | Amount in Words: | #REF! |  | Bank Address | #REF!
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF! | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF!
| Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF! | Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF!
|  |  |  | Routing Instructions: | #REF! |  |  |  | Routing Instructions: | #REF!
| Payee 4: |  |  |  |  | Payee 4:
| Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF! | Beneficiary Name: | #REF! |  | Owner of Bank Account: | #REF!
| Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF! | Currency in which beneficiary should receive the funds | #REF! |  | Owner of Bank Account: | #REF!
| Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF! | Amount in currency in which beneficiary should receive the funds: | #REF! |  | Bank Account Number: | #REF!
| Amount in Words: | #REF! |  | Bank Address | #REF! | Amount in Words: | #REF! |  | Bank Address | #REF!
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF! | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) | #REF! |  | Bank SWIFT Code: | #REF!
| Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF! | Equivalent in grant currency (Calculated based on the indicated exchange rate) | #REF! |  | Bank Code (Other): | #REF!
|  |  |  | Routing Instructions: | #REF! |  |  |  | Routing Instructions: | #REF!

## LFA_Annex-SR Financials
LFA On-going Progress Review and Disbursement Recommendation
Annex to PU/DR - LFA-reviewed Sub-recipient financial information ! Completion of this table by the PR and verification by the LFA are discretionary, and should be done upon the Secretariat's request.
Grant number: |  |  |  | GEO-H-NCDC
Progress Update - Reporting Period: |  |  |  | Cycle: | Semester |  | Number: | 2
Progress Update - Period Covered: |  |  |  | Beginning Date: | 2014-07-01 |  | End Date: | 2014-12-31
Progress Update - Number: |  |  |  | 2
Currency: |  |  |  | EUR
Note for LFAs: The information below is displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* |  | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Cumulative Actual Expenditure through period covered by this Progress Update | Cash balance at the end of the period covered by this Progress Update | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (1) between cumulative budget and cumulative expenditure and (2) between cumulative disbursement and cumulative expenditure (mandatory for amounts above $50,000 or equivalent and with more than 10% variance) | LFA Comments on the PR's overall verification efforts of SR expenditure and the explanations of variance provided | Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Latest Cumulative Actual Expenditure (as per most recent SR reports available at PR level) | End date of period covered in most recent SR report | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (mandatory for amounts above $50,000 and with more than 10% variance)
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
TOTAL |  |  | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  |  |  | TOTAL |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
*TOTAL amount for these columns should reconcile with relevant amounts under "1b Disbursed to Sub Recipients" in Section 3A"
** Where the number of SRs is significant (over 10), SRs with small budgets (less than $50,000 or EUR equivalent cumulative each) do not need to be reported separately and the figures can be aggregated in a group called "Other Minor SRs"

## Annex for additional info
Annex 1 | Use these worksheets to provide more detailed information on EFR variances if necessary

## Memo HIV (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
Please select… | Please select… | Please select… | Please select… | Please select… |  | Please select…
Prevention: Behavioral Change Communication - Mass media | % of young women and men aged 15-24 who are HIV infected | impact | % of young people aged 15-24 who had sex with more than one partner in the last year | National Health Accounts | Please enter a corresponding indicator here… | Please select disease and Impact/Outcome first
Prevention: Behavioral Change Communication - community outreach | % of adults aged 15-49 who are HIV infected | outcome | % of young people aged 15-19 who have never had sex | DHS/DHS+ (Demographic and Health Survey) | Please enter a data source here…
Prevention: Condom distribution | % of adults and children with HIV still alive 12 months after initiation of antiretroviral therapy (extend to 2, 3, 5 years as program matures) |  | % of young people aged 15-24 who never had sex in the last year of those who ever had sex | MICS (Multiple Indicator Cluster Survey) | Please enter a SDA here…
Prevention: Counseling and Testing | % of infants born to HIV infected mothers who are infected |  | % of young people aged 15-24 reporting the consistent use of a condom with non-regular sexual partners in the last year | AIS (AIDS Indicator Survey)
Prevention: PMTCT | % of most-at-risk population(s) (sex workers, clients of sex workers, men who have sex with men, injecting drug users) who are HIV infected |  | % of young women and men who had sex before the age of 15 | SAMS (Service Availibility Mapping Survey)
Prevention: Post-exposure prophylaxis (PEP) | % of HIV seroprevalence among all newly registered TB patients |  | % of adults and children who are still on treatment after 6 months, 1, 2, 3, 5 years from the initiation of treatment | BSS (Behavioral and Surveillance Survey)
Prevention: STI diagnosis and treatment |  |  | % of injecting drug users who have adopted behaviors that reduce transmission of HIV. | Sentinel surveillance
Prevention: Blood safety and universal precaution |  |  | % of orphaned children compared to non-orphaned children aged 10-14 who are currently attending school | Serological surveys
Treatment: Antiretroviral treatment (ARV) and monitoring |  |  | % of young people aged 15-24 reporting the use of a condom the last time they had sex with a non-regular sexual partner | Prevalence surveys
Treatment: Prophylaxis and treatment for opportunistic infections |  |  | % of people expressing accepting attitudes towards PLWHA, of all people surveyed aged 15-49 | Facility-based survey
Care and support: Care and support for the chronically ill |  |  | % of female sex workers reporting the use of a condom with every client in the last month | Key informant survey
Care and support: Support for orphans and vulnerable children |  |  | % of men who have had sex with a female sex worker in the last year | Specific surveys (to be defined)
TB/HIV collaborative activities: HIV care and support for HIV-positive TB patients | TB/HIV collaborative activities: Intensified case-finding among PLWHA |  | % of men reporting the use of condom the last time they had anal sex with a male partner in the last 6 months | Civil registration systems (vital/disease specific registration)
Supportive environment: Policy development including workplace policy | TB/HIV collaborative activities: Prevention of TB disease in PLWHA |  |  | Census
Supportive environment: Strengthening of civil society and institutional capacity building | TB/HIV collaborative activities: Prevention of HIV in TB patients |  |  | Health service statistics
Supportive environment: Stigma reduction in all settings | TB/HIV collaborative activities: Prevention of opportunistic infections in PLWHA with TB |  |  | Patient register
Supportive environment: Program management and administration |  |  |  | Clinical cohort follow-up studies
HSS: Service delivery | TB/HIV collaborative activities: Provision of antiretroviral treatment for TB patients during TB treatment |  |  | Community services assessment
HSS: Human resources | HSS: PAL (Practical Approach to Lung Health) |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: Community Systems Strengthening |  |  |  | Operational research
HSS: Information system & Operational research
HSS: Infrastructure
HSS: Procurement and Supply management
HSS: Other, specify

## Memo TB (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Improving diagnosis | TB prevalence rate | impact | Case detection | National Health Accounts
Standardized treatment, patient support and patient charter | TB incidence rate | outcome | Treatment success rate | DHS/DHS+ (Demographic and Health Survey)
Procurement and supply management | TB mortality rate |  | Smear conversion rate | MICS (Multiple Indicator Cluster Survey)
M&E |  |  |  | AIS (AIDS Indicator Survey)
TB/HIV |  |  |  | SAMS (Service Availibility Mapping Survey)
MDR-TB |  |  |  | BSS (Behavioral and Surveillance Survey)
High-risk groups |  |  |  | Sentinel surveillance
HSS (beyond TB) |  |  |  | Serological surveys
PAL (Practical Approach to Lung Health) |  |  |  | Prevalence surveys
PPM / ISTC (Public-Public, Public-Private Mix (PPM) approaches and International standards for TB care) |  |  |  | Facility-based survey
ACSM (Advocacy, communication and social mobilization) |  |  |  | Key informant survey
Community TB care |  |  |  | Specific surveys (to be defined)
Programme-based operational research
Other:Specify
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
Census
Health service statistics
Patient register
Clinical cohort follow-up studies
Community services assessment
Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
Operational research
R&R TB system, quarterly report
R&R TB system, yearly management report
Other Surveillance reports, specify

## Memo Malaria (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Prevention: Behavioral Change Communication - Mass media | Death rates associated with Malaria: all-cause under-5 mortality rate in highly endemic areas | impact | % of U5 children (and other target groups) with malaria/fever receiving appropriate treatment within 24 hours (community/health facility) | National Health Accounts
Prevention: Behavioral Change Communication - community outreach | Incidence of clinical malaria cases (estimated and/or reported) | outcome | % of U5 children (and other target group) with uncomplicated malaria correctly managed at health facilities | DHS/DHS+ (Demographic and Health Survey)
Prevention: Insecticide-treated nets (ITNs) | Anaemia prevalence in children under 5 years of age |  | % of U5 children (and other target groups) admitted with severe malaria and correctly managed at health facilities | MICS (Multiple Indicator Cluster Survey)
Prevention: Malaria prevention during pregnancy | Prevalence of malaria parasite infection |  | % of children U5 sleeping under an ITN the previous night | MIS (Malaria Indicator Survey)
Prevention: Vector control (other than ITNs) | Laboratory-confirmed malaria cases seen in heath facilities |  | % of households with at least one ITN | SAMS (Service Availibility Mapping Survey)
Prevention: other - specify | Laboratory-confirmed malaria deaths seen in health facilities |  | % of pregnant women (and other target groups) sleeping under an ITN the previous night | BSS (Behavioral and Surveillance Survey)
Treatment: Prompt, effective anti-malarial treatment | Malaria-attributed deaths in sentinel demographic surveillance sites |  | % of pregnant women on Intermittent preventive treatment (IPT) according to national policy (specific to Sub-Saharian Africa) | Sentinel surveillance
Treatment: Home based management of malaria | API (Annual Parasite Index) (specific to Latin America and Asia) |  | % of households in malaria areas protected by IRS | MOH (routine HIS or HMIS)
Treatment: Diagnosis |  |  |  | RBM (Roll Back Malaria)
Treatment: other - specify |  |  |  | Serological surveys
Supportive environment: Monitoring drug resistance |  |  |  | Prevalence surveys
Supportive environment: Monitoring insecticide resistance |  |  |  | Facility-based survey
Supportive environment: Coordination and partnership development (national, community, public-private) |  |  |  | Key informant survey
Supportive environment: other - specify |  |  |  | Specific surveys (to be defined)
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
HSS: Service delivery |  |  |  | Census
HSS: Human resources |  |  |  | Health service statistics
HSS: Community Systems Strengthening |  |  |  | Patient register
HSS: Information system & Operational research |  |  |  | Clinical cohort follow-up studies
HSS: Infrastructure |  |  |  | Community services assessment
HSS: Procurement and Supply management |  |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: other - specify |  |  |  | Operational research
Questionnaire

## Definitions-lists-EFR (hidden)
Please Select…
Prevention
Treatment
Care and Support
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention
Treatment
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention: Behavioral Change Communication - Mass Media
Prevention: Behavioral Change Communication - Community Outreach
Prevention: Insecticite-treated nets (ITNs)
Prevention: Malaria in pregnancy
Prevention: Vector control (other than ITNs)
Prevention: Other - specify
Treatment: Prompt, effective antimalatial treatment
Please Select…
TB Detection
TB Treatment
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening
Please Select…
Improving diagnosis
Standardized treatment, pation support and patient charter
Procurement and Supply management
M&E
TB/HIV
MDR-TB
High-risk groups
Please Select…
FBO
NGO/CBO/Academic
Private Sector
Ministry Health (MoH)
Other Government
UNDP
Other Multilateral Organization